## Av_vs_supplied
Resource ID | Activity ID | Activity Name | Original Duration | Actual Duration | Remaining Duration | Deviated Duration | Planned Start | Planned Finish | Start | Finish | Actual Finish | Budgeted Units | Actual Units | Date of receiving units supplied by client | Available units at site received by client | Available units supplied by client vs Actual units of activities | Remaining Units | Units % Complete | Budgeted Units / Time | Drive Activity Dates | Reason for Delay | Responsibility
BIG.Q.Rft | CON-B03-FOOT-1050 | RFT for RC Raft & Footings (B03) (footing) | 10 | 10 | 0 | -8 | 2026-01-01 | 2026-01-13 | 10-Jan-26 A | 2026-01-21 | Finished | 196.86 | 196.86 | 2025-12-09 | 586.98 | 390.12 | 0 | 100% | 19.69/d | Yes
BIG.Q.Rft | CON-B04-WT-1070 | RFT for RC Raft (B04) (Water Tank) | 5 | 6 | 0 | 2 | 2026-01-14 | 2026-01-19 | 10-Jan-26 A | 2026-01-17 | Finished | 45.81 | 45.81 |  |  | 344.31 | 0 | 100% | 9.16/d | Yes
BIG.Q.Rft | CON-B02-FOOT-1050 | RFT for RC Raft & Footings (B02) (footing) | 10 | 4 | 0 | -7 | 2026-01-03 | 2026-01-14 | 17-Jan-26 A | 2026-01-21 | Finished | 155.42 | 155.42 |  |  | 188.89 | 0 | 100% | 15.54/d | Yes
BIG.Q.Rft | CON-B03-FOOT-1070 | RFT for Columns & Walls Below SOG (B03) (footing) | 5 | 31 | 0 | -48 | 2026-01-08 | 2026-01-13 | 26-Jan-26 A | 2026-03-02 | Finished | 1.46 | 1.46 |  |  | 187.43 | 0 | 100% | 0.29/d | Yes
BIG.Q.Rft | CON-B02-FOOT-1070 | RFT for Columns & Walls Below SOG (B02) (footing) | 6 | 30 | 0 | -50 | 2026-01-06 | 2026-01-13 | 28-Jan-26 A | 2026-03-04 | Finished | 2.43 | 2.43 |  |  | 185 | 0 | 100% | 0.41/d | Yes
BIG.Q.Rft | CON-B01-FOOT-1050 | RFT for RC Raft & Footings (B01) (footing) | 14 | 11 | 0 | 0 | 2026-02-02 | 2026-02-17 | 05-Feb-26 A | 2026-02-17 | Finished | 320.45 | 320.45 |  |  | -135.45 | 0 | 100% | 22.89/d | Yes
BIG.Q.Rft | CON-B01-FOOT-1070 | RFT for Columns & Walls Below SOG (B01) (footing) | 8 | 62 | 1 | -93 | 2026-02-05 | 2026-02-14 | 28-Feb-26 A | 2026-05-18 |  | 1.98 | 1.68 | 2026-02-14 | 371.115 | 233.985 | 0.3 | 85% | 0.25/d | Yes
BIG.Q.Rft | CON-B03-BAS02-1010 | RFT for Walls, Col. & Cores (B03) (Bas 02) | 12 | 5 | 0 | 40 | 2026-04-06 | 2026-04-20 | 05-Mar-26 A | 2026-03-11 | Finished | 28.19 | 28.19 |  |  | 205.795 | 0 | 100% | 2.35/d | Yes
BIG.Q.Rft | CON-B04-WT-1110 | RFT for Walls (B04) (Water Tank) | 8 | 27 | 0 | 2 | 2026-04-07 | 2026-04-16 | 08-Mar-26 A | 2026-04-14 | Finished | 40.71 | 40.71 |  |  | 165.085 | 0 | 100% | 5.09/d | Yes
BIG.Q.Rft | CON-B04-FOOT-1050 | RFT for RC Raft & Footings (B04) (footing) | 8 | 53 | 3 | -71 | 2026-03-01 | 2026-03-09 | 10-Mar-26 A | 2026-05-19 |  | 296.46 | 192.7 |  |  | -27.615 | 103.76 | 65% | 37.06/d | Yes
BIG.Q.Rft | CON-B04-FOOT-1070 | RFT for Columns & Walls Below SOG (B04) (footing) | 5 | 53 | 2 | -42 | 2026-04-01 | 2026-04-06 | 10-Mar-26 A | 2026-05-18 |  | 3.14 | 2.04 |  |  | -29.655 | 1.1 | 65% | 0.63/d | Yes
BIG.Q.Rft | CON-B02-BAS02-1010 | RFT for Walls, Col. & Cores (B02) (Bas 02) | 12 | 12 | 0 | 0 | 2026-04-21 | 2026-05-04 | 21-Apr-26 A | 2026-05-04 | Finished | 21.08 | 21.08 | 2026-05-04 | 355.84 | 334.76 | 0 | 100% | 1.76/d | Yes