## From SAMCO to ACE
Ref No | Date | Type | Subject | Main Purpose | Key Requests | Scope Impact | Responsibility | Affected Activities | Start Dependency | Sequence Impact | Commercial Impact | Risk Type | Risk Owner | Delay Risk | EOT Potential | Claim Strength | Required Actions
BD-CW-SAMCO-ACE-LET-STR-001 | 20-May-2025 | Delegation | Delegation of Authority | Authorize SAMCO representative for project matters | Acknowledge delegated authority |  | SAMCO | Project administration |  |  |  | Administrative | SAMCO |  |  |  | Record authorized representative
BD-CW-SAMCO-ACE-LET-STR-002 | 30-Jun-2025 | Delegation | Delegation of Authority | Update/confirm SAMCO authorized representative | Acknowledge Eng. Ahmed El Geady authority |  | SAMCO | Project administration |  |  |  | Administrative | SAMCO |  |  |  | Update correspondence matrix
BD-CW-SAMCO-ACE-LET-STR-003 | 30-Jun-2025 | Response / Reservation | RE: Outstanding Deliverables - Urgent Response Required | Respond to ACE-PM notices on overdue deliverables and delay items | Confirm TC1 installed, request soil replacement completion schedule, submit PM CV, reserve baseline dependency | No new scope; start tied to soil replacement by others | Shared: SAMCO for submittals, Employer/others for soil works | Tower cranes, baseline program, shop drawings, soil replacement, steel inventory | Completion of soil replacement and confirmed start date | High impact on baseline and start of works | Potential prolongation if dependencies remain unresolved | Schedule / Interface | Shared | High | Moderate | Moderate | Close outstanding submittals and issue confirmed soil replacement schedule
BD-CW-SAMCO-ACE-LET-STR-004 | 28-Aug-2025 | Notice / Site Condition | RE: Site Survey Findings and Allocation of Concrete Batching Plant | Record survey deviations, ramp changes, batching plant location, and Zone 2 handover conditions | Review survey findings, approve guidance, accept owner cost/time if batching plant relocated | Site boundaries, ramp, batching plant and Zone 2 handover affected | Owner/Engineer for handover/location; SAMCO for execution after access | Boundary excavation, ramp works, batching plant, Zone 2 works | Full land handover; Zone 2 commencement three months after handover | Medium to High, especially Zone 2 | Possible relocation cost and time extension | Site Access / Interface | Shared / Owner | High | Moderate to High | Moderate | Issue final survey decisions and confirm batching plant/ramp instructions
BD-CW-SAMCO-ACE-LET-STR-005 | 10-Sep-2025 | Notice of Delay / Site Obstacle | RE: Documentation of Site Obstacles Affecting Project Progress | Document water leakage and inability to complete testing/excavation | Resolve leakage, notify when clear, exclude affected period from contract duration | No scope change; site condition obstructs works | Owner/Engineer for utility issue; SAMCO to resume after clearance | DCPT, open pits, tank survey, excavation | Leakage repair and safe site access | High for affected testing/excavation sequence | Potential prolongation and remediation cost | Site Condition / Delay | Owner / Shared | High | Moderate to High | Moderate | Repair leakage, document affected period, update recovery plan
BD-CW-SAMCO-ACE-LET-STR-006 | 22-Sep-2025 | Response | RE: Response to Letter No. BD-ACEPM-SAMCO-LET-004 | Confirm contractual submissions are being completed | Submit staff, schedule, HSE, QAP, BBS and reports progressively | No scope impact | SAMCO | Pre-construction submittals and reporting | Contractual submission cycle | Medium if approvals lag | Low direct commercial impact | Contract Compliance | SAMCO | Medium | Low | Weak | Submit remaining contractual documents
BD-CW-SAMCO-ACE-LET-STR-007 | 24-Sep-2025 | Response / Reservation | RE: Response to Letter No. BD-ACEPM-SAMCO-LET-005 | Respond to ACE-PM rejection of site obstacle position | Confirm tests resumed/completed, state approvals route, reserve contractual claims | No scope change; records time effects from leakage | Shared | Soil tests, grid leveling, excavation drawings, reporting | Leakage repair and consultant approvals | Medium | Potential future claim if substantiated | Site Condition / Contract | Shared | Medium | Conditional | Moderate | Track approvals and submit any claim with particulars
BD-CW-SAMCO-ACE-LET-STR-008 | 24-Sep-2025 | Claim Notice / Reservation | Response Regarding Site Ramp Modification Works | Reserve entitlement for ramp modification works outside original scope | Recognize cost and time compensation for ramp widening/level changes | Potential additional access route works | Employer/Engineer if instructed; SAMCO if accepted as access obligation | Service ramp, material access, site logistics | Engineer instruction and agreed compensation basis | Medium | Additional payment and EOT claimed | Access / Variation | Shared | Medium | Conditional | Moderate | Issue determination on ramp scope and compensation
BD-CW-SAMCO-ACE-LET-STR-009 | 24-Sep-2025 | Submittal | Submission of Consultant CV and Approval Certificate | Submit nominated design review consultant details | Approve consultant CV and syndicate certificate | No construction scope impact | SAMCO / Engineer | Design review consultant appointment | Engineer approval before design review | Medium if approval delays design review | Low direct; possible delay if rejected | Technical / Approval | Shared | Medium | Low to Moderate | Weak to Moderate | Review and approve/reject consultant submittal
BD-CW-SAMCO-ACE-LET-STR-010 | 25-Sep-2025 | Procurement Request | Supply of reinforcement steel for the project | Request first delivery of reinforcement steel | Supply listed steel quantities by diameter | No scope change; material supply obligation triggered | Owner / Employer supply arrangement | Reinforcement procurement and early structural works | Owner steel supply before fabrication/installation | Medium | Potential delay and self-procurement cost if late | Procurement | Owner | Medium | Conditional | Moderate | Confirm and deliver first steel order
BD-CW-SAMCO-ACE-LET-STR-011 | 29-Sep-2025 | Procurement Revision / Coordination | Request to Reduce First Reinforcement Steel Delivery | Adjust steel order due to site constraints and revised active workface | Reduce first delivery to raft/tank wall dowels; later submit second delivery | No scope change; sequencing and storage adjusted | Shared | Steel supply, B1-B4 excavation/soil replacement | Official handover of obstruction-free boundaries | Medium | Avoids storage damage; may affect procurement sequence | Procurement / Site Logistics | Shared | Medium | Conditional | Moderate | Approve revised quantities and coordinate later delivery
BD-CW-SAMCO-ACE-LET-STR-012 | 30-Sep-2025 | Meeting Follow-up | Meeting Minutes and Follow-up on Discussed Points | Record 25-Sep meeting outcomes and open actions | Provide missing design packages, signboard decision, B1-B4 boundaries/levels, pipe repair update | Potential design/access/interface impact | Owner/Engineer for data and handover; SAMCO for follow-up | Design review, boundary marking, tank works, excavation | Owner contractor completion and complete design package | High for affected work fronts | Potential delay and disruption if unresolved | Interface / Design / Site Access | Shared / Owner | High | Moderate | Moderate | Issue missing drawings, boundaries, repair status and instructions
BD-CW-SAMCO-ACE-LET-STR-013 | 30-Sep-2025 | Notice of Suspension | Pipe Breakage and Suspension of Excavation Works | Notify pipe breakage stopped excavation/spoil removal | Repair pipes and address resulting damage before resumption | No scope change; remedial works may arise | Owner/Engineer for utility repair; SAMCO to resume after clearance | Tank excavation, spoil removal, B5/B6/B14/B15 area | Pipe repair and damage rectification | High on tank excavation | Potential delay and remedial cost | Utility / Site Condition | Owner / Shared | High | Moderate to High | Moderate | Repair pipes, document damage, confirm restart date
BD-CW-SAMCO-ACE-LET-STR-014 | 05-Oct-2025 | Notice / Reservation | Implications of Water Pipe Break | Reserve no responsibility and record impact on backfilling/boreholes | Seek guidance, technical tests, consultant recommendations and settlement of extra quantities | Potential additional backfilling/remedial scope | Owner/Engineer for utility damage and instructions; SAMCO if formally assigned | Backfilling, verification boreholes, affected rear area | Safe remediation and geotechnical confirmation | High for affected area | Extra quantities and possible delay entitlement | Utility / Geotechnical / Commercial | Owner / Shared | High | Moderate to High | Moderate to Strong | Issue technical instruction, remove obstacles, measure extra works
BD-CW-SAMCO-ACE-LET-STR-015 | 06-Oct-2025 | Document Request | Reminder to Submit Final Package and Signed Hard Copies | Request complete IFC package to support variation notice process | Provide approved stamped structural, architectural and MEP IFC drawings | No direct scope change; enables clash review and notices | Engineer / Employer | Design review, clash detection, variation notices | Complete approved IFC package | Medium | Potential loss/late variation notice if not provided | Design / Contract Notice | Engineer / Employer | Medium | Conditional | Moderate | Transmit complete stamped IFC package
BD-CW-SAMCO-ACE-LET-STR-016 | 07-Oct-2025 | Contract Position / Reservation | Clarification Regarding Coordination Responsibilities | Clarify SAMCO responsibility excludes MEP works by employer-appointed subcontractors | Provide MEP drawings/materials via MEP subcontractor or issue VO if SAMCO must execute | Potential new MEP/interface scope if instructed | Employer/MEP subcontractor; SAMCO coordination only unless varied | MEP flanges, sleeves, tie-ins, shop drawings | Appointment/input from MEP contractor or formal variation | High if MEP interfaces block structural works | Potential variation cost/time | Scope / Interface | Employer / Shared | High | Moderate | Moderate | Appoint/coordinate MEP contractor or issue formal variation
BD-CW-SAMCO-ACE-LET-STR-017 | 09-Oct-2025 | Variation Response / Rejection | Response to VI ROYA-BIG-2025-VI-001 | Reject utility protection/supporting works as excluded from contract | Treat utility protection as compensated variation with time impact | Additional utility protection works outside priced scope | Employer/Engineer if instructed; SAMCO after variation agreement | Existing utilities, protection works, high-risk areas | Formal VI, agreed methodology and valuation | High if protection required before excavation/structure | Additional payment and EOT claimed | Variation / Utility | Employer / Shared | High | Moderate to High | Strong | Issue proper VI, define method, value cost/time
BD-CW-SAMCO-ACE-LET-STR-018 | 13-Oct-2025 | Response / Delay Mitigation | Response Regarding Delay of Works at Site | Explain reasons soil replacement had not fully started | Provide instruction on proceeding without test results; consider ramp/test/geogrid timing | No new scope; execution constrained by tests/ramp/access | Shared | B1/B2 soil replacement, ramps, geogrid/geocell procurement | Test results, service ramp repair, clear handover | High for soil replacement start | Potential delay if tests/instructions delayed | Schedule / Site Logistics | Shared | High | Moderate | Moderate | Give instruction on material execution and expedite ramp/test approvals
BD-CW-SAMCO-ACE-LET-STR-019 | 26-Oct-2025 | Design Request | Request for Complete Set of IFC Drawings | Request full IFC set after major design changes observed | Provide approved architectural, structural, mechanical and electrical IFC drawings | Potential design change impact | Engineer / Employer | Design review, coordination, program update | Complete IFC package | High | Possible time/cost if changes affect works | Design Information | Engineer / Employer | High | Moderate | Moderate to Strong | Issue complete coordinated IFC package
BD-CW-SAMCO-ACE-LET-STR-020 | 27-Oct-2025 | Status Update / Reservation | Project Status Update - Buildings B1 to B17 | Record current status and constraints across project zones | Provide missing IFC/MEP data, confirm MEP contractor, resolve holds | No direct scope; identifies constraints | Shared | B1-B17 works, tank, replacement soil, drawings | Missing drawings, MEP appointment, soil results | Medium to High | Potential delay if constraints persist | Progress / Interface | Shared | Medium to High | Conditional | Moderate | Close missing data and unblock held areas
BD-CW-SAMCO-ACE-LET-STR-021 | 29-Oct-2025 | Insurance Undertaking | Contractor Commitment to Maintain Required Insurance | Undertake compliance with contractual insurance requirements | Accept contractor liability for gaps, deductibles and deviations | No scope impact | SAMCO | Insurance coverage, site risk | Policy issuance/maintenance | Low direct | Potential uninsured loss borne by SAMCO | Insurance / Contract | SAMCO | Low |  |  | Maintain compliant policies and originals
BD-CW-SAMCO-ACE-LET-STR-022 | 23-Nov-2025 | Status Update / Reservation | Project Status Update - Buildings B1 to B17 | Update progress and identify pending approvals/data | Provide design review approval, MEP/basement drawings, BOQ, soil feedback | No new scope; highlights holds | Shared | B1-B17, tank, waterproofing, soil replacement | Approvals, drawings and soil reports | Medium to High | Potential delay if pending items remain | Progress / Design / Geotechnical | Shared | Medium to High | Conditional | Moderate | Issue pending approvals and missing documents
BD-CW-SAMCO-ACE-LET-STR-023 | 23-Nov-2025 | Technical Query | Related to Waterproofing Works | Seek clarification on waterproofing system needed for 10-year warranty | Confirm insulation materials/system to use | Possible upgraded waterproofing specification | Engineer / Consultant | Basement/tank waterproofing | Material/system clarification before execution | Medium | Potential additional cost for upgraded system | Technical / Variation | Engineer / Employer | Medium | Conditional | Moderate | Confirm waterproofing system and approve revised submittal
BD-CW-SAMCO-ACE-LET-STR-024 | 24-Nov-2025 | Variation Rejection | Response to VI BD-ACEPM-SAMCO-VI-0003 | Reject execution of MEP works as outside SAMCO scope | Appoint qualified MEP contractor; limit SAMCO to coordination | Potential MEP first-fix/interface scope disputed | Employer/MEP contractor; SAMCO coordination only | MEP first fix, flanges/sleeves, tank interfaces | MEP contractor appointment or formal change | High | Potential time/cost if MEP not appointed | Scope / Variation | Employer / Shared | High | Moderate | Moderate | Resolve scope and appoint/authorize MEP execution
BD-CW-SAMCO-ACE-LET-STR-025 | 26-Nov-2025 | Procurement Request | Supply of Reinforcement Steel - Second Delivery | Request second reinforcement steel delivery | Supply listed steel quantities | No scope change | Owner / Employer supply arrangement | Reinforcement procurement and fabrication | Owner steel supply | Medium | Potential delay if supply late | Procurement | Owner | Medium | Conditional | Moderate | Confirm and deliver second steel order
BD-CW-SAMCO-ACE-LET-STR-026 | 30-Nov-2025 | Technical Meeting Request | Reply of Design Review | Request urgent meeting to resolve design review comments | Hold meeting 02-Dec with owner/designer/consultants; approve final designs | No direct scope; may lead to design changes | Engineer / Employer / Designers | Raft foundation, reinforcement preparation, design review | Resolution before raft reinforcement | High | Potential delay if final design not approved | Design / Coordination | Shared / Employer | High | Moderate | Moderate | Arrange meeting and close design comments
BD-CW-SAMCO-ACE-LET-STR-027 | 30-Nov-2025 | Formal Rejection / Reservation | Formal Rejection of Assigning MEP Works | Set SAMCO position that MEP is outside civil/structural scope | Withdraw MEP assignment, appoint MEP contractor, record SAMCO non-responsibility for delays | MEP scope disputed as outside contract | Employer/MEP contractor; SAMCO coordination only | MEP first fix, tank interfaces, structural continuity | MEP contractor appointment or agreed VO | High | Potential prolongation/variation if MEP assigned | Scope / Contract | Employer / Shared | High | Moderate | Moderate | Issue scope determination and MEP execution route
BD-CW-SAMCO-ACE-LET-STR-028 | 06-Dec-2025 | Payment Submission | Submission of Interim Payment Certificate No. 1 | Submit IPC No. 1 for review and approval | Review and approve IPC 1 | No scope impact | Engineer / Employer for certification/payment | Payment certification | Submission of IPC | Low schedule, high cash-flow relevance | Payment due under contract | Commercial / Payment | Employer / Engineer | Low | Conditional |  | Certify and pay IPC 1
BD-CW-SAMCO-ACE-LET-STR-029 | 07-Dec-2025 | Design Reservation | Design Review | Clarify design modifications are outside SAMCO obligation and affect start readiness | Resolve design comments at least 10 days before reinforcement; allow 20 days for major redesign | Potential redesign or shop drawing rework | Designer/Engineer for design; SAMCO for review/execution | Design review, shop drawings, raft reinforcement | Final approved design and closed comments | High | Potential time/cost for redesign or rework | Design / Schedule | Employer / Designer | High | Moderate | Moderate | Close design review comments and confirm design basis
BD-CW-SAMCO-ACE-LET-STR-030 | 11-Dec-2025 | Response / Design Reservation | Re: Design Review | Explain incomplete design packages delayed comprehensive review | Provide latest complete structural, architectural and MEP IFC packages and resolve design status | Potential design/information delay | Engineer / Employer | Design review, IFC coordination, program | Complete design information | High | Potential delay if incomplete information persists | Design Information | Engineer / Employer | High | Moderate | Moderate to Strong | Issue coordinated complete IFC set and final design instruction
BD-CW-SAMCO-ACE-LET-STR-031 | 11-Dec-2025 | Weather Notice | Postponement of Insulation Works Due to Weather | Notify insulation start postponed due rain/weather | Resume after surface dryness and safe conditions | No scope change | Weather / SAMCO safety decision | Waterproofing/insulation works | Suitable weather and dry surface | Low to Medium | Minor productivity impact | Weather / Safety | Shared / Force Majeure-like | Low | Low / Conditional | Weak | Record weather and resume when suitable
BD-CW-SAMCO-ACE-LET-STR-032 | 11-Dec-2025 | Design Request | Request for Complete Package for Coordination - TRA-007 | Request missing basement/foundation MEP package | Provide complete lower-level electrical, HVAC and mechanical drawings | No direct scope; enables coordination | Engineer / Employer / Designers | MEP coordination, basement/foundation interfaces | Complete MEP package | Medium to High | Potential delay to coordinated shop drawings | Design Information / Interface | Engineer / Employer | Medium to High | Conditional | Moderate | Issue missing basement/foundation MEP package
BD-CW-SAMCO-ACE-LET-STR-033 | 15-Dec-2025 | Response / Reporting Position | Response to LET-021 Periodic Reports | Explain contractual reports require approved baseline schedule | Approve/comment time schedule, align reporting format, continue daily reports | No scope impact | Shared | Progress reporting, time schedule, controls | Approved baseline programme | Medium | Potential IPC/reporting dispute | Contract Administration | Shared | Medium | Low to Moderate | Weak to Moderate | Close programme comments and agree report template
BD-CW-SAMCO-ACE-LET-STR-034 | 17-Dec-2025 | Design Review / Reservation | Re: Design Review | Transmit NECB design review outcome and seek decision on criteria | Confirm whether to proceed with Prime criteria or redesign under NECB criteria | Possible major redesign if conservative criteria adopted | Employer/Designer/Engineer | Structural design, foundations, columns, slabs, beams | Decision on adopted design criteria | High | Major cost/time if redesign required | Design / Technical | Employer / Designer | High | High if redesign | Strong if criteria/design changed | Issue formal design criteria decision and redesign instruction if needed
BD-CW-SAMCO-ACE-LET-STR-035 | 18-Dec-2025 | Variation Rejection / Contract Position | Response to LET-019 and VI-0003 | Reiterate flanges are MEP/mechanical and outside civil scope | Appoint MEP contractor; reject VI-0003; reserve rights | MEP/flange scope disputed | Employer/MEP contractor | Ground water tank flanges, MEP interfaces | Scope determination or formal compensated VO | High | Potential variation and delay cost | Scope / Variation | Employer / Shared | High | Moderate | Moderate | Resolve disputed scope and issue formal instruction/valuation
BD-CW-SAMCO-ACE-LET-STR-036 | 21-Dec-2025 | Variation Request | Request for VI - CPTu and DCPT Works | Request variation instruction and payment for extra geotechnical tests | Issue VI for CPTu and compensate CPTu/DCPT test points | Additional testing scope | Owner/Engineer if instructed; SAMCO for execution | CPTu, DCPT, B6/B14/B15 soil verification | Owner consultant request/test instruction | Low to Medium | Additional measured cost | Variation / Geotechnical | Employer / Shared | Low to Medium | Low / Conditional | Moderate | Issue VI and agree valuation
BD-CW-SAMCO-ACE-LET-STR-037 | 24-Dec-2025 | Status Update / Request | Project Status Update - Buildings B1 to B17 | Update progress and list blockers across groups | Provide MEP package, BOQ, missing drawings and soil feedback | No direct scope; identifies holds | Shared | B1-B17, tank, soil, waterproofing, steel fabrication | Missing MEP/BOQ/drawings/soil approvals | Medium to High | Potential delay if blockers remain | Progress / Interface | Shared | Medium to High | Conditional | Moderate | Close blockers and issue pending information
BD-CW-SAMCO-ACE-LET-STR-038 | 21-Jan-2026 | Payment Recommendation / Attachment | ACEPM Recommendation of Monthly Interim Payment No. 2 | Record ACEPM recommended IPC No. 2 amount and deductions | Proceed with Roya action/payment based on recommendation | No scope impact | ACEPM / Roya / Employer | IPC 2 certification/payment | Technical/commercial review of IPC | Low schedule, cash-flow impact | Payment certification affects cash flow | Commercial / Payment | Employer / Engineer | Low | Conditional |  | Process recommended IPC 2 payment
BD-CW-SAMCO-ACE-LET-STR-039 | 04-Jan-2026 | Notice / Site Incident | Water Pipeline Leakage and Its Impact on Project Works | Document 31-Dec leakage and 01-Jan sanitary pipe damage | Recognize additional works and responsibility limits | Possible remedial/rework scope | Owner/utility repair team; SAMCO for mitigation/rework if instructed | Formwork, plain raft preparations, trench/diversion, pipeline area | Utility repair and clearance | Medium | Potential rework and additional cost | Utility / Site Condition | Owner / Shared | Medium | Conditional | Moderate | Assess damage, instruct/measure rework, prevent recurrence
BD-CW-SAMCO-ACE-LET-STR-040 | 05-Jan-2026 | Reservation / Design Instruction Request | Continuation of Works and Final Written Instructions | Confirm continuation under approved design while reserving rights | Issue final written instructions and accept design responsibility boundaries | No immediate scope; future redesign may vary works | Employer/Designer for design; SAMCO for execution | B1-B4 design review, approved designs, structural works | Written instruction/design confirmation | High if later design changes | Potential EOT/cost for future redesign | Design / Contract | Employer / Designer | Medium to High | Conditional High | Strong if later change occurs | Issue clear written instruction/design confirmation
BD-CW-SAMCO-ACE-LET-STR-041 | 06-Jan-2026 | Urgent Notice / Conditional Proposal | Critical Interface Issue on Critical Path | Notify sewage pipeline conflict through tank base slab and offer temporary mitigation | Provide approved MEP docs, supervision, written approval and VO/payment terms | Temporary MEP/interface works within tank raft | Employer/MEP consultant; SAMCO only if authorized | Tank base slab, sewage pipeline, MEP first fix, concrete casting | Written instruction, approved drawings/specs, MEP supervision | High critical path impact | Cost reimbursement/VO and possible delay | Interface / MEP / Critical Path | Employer / Shared | High | High | Strong if instruction delayed | Issue urgent VO/instruction and approved technical package
BD-CW-SAMCO-ACE-LET-STR-042 | 06-Jan-2026 | Procurement Request | Supply of Reinforcement Steel - Third Delivery | Request third reinforcement steel delivery | Supply listed steel quantities | No scope change | Owner / Employer supply arrangement | Reinforcement procurement and fabrication | Owner steel supply | Medium | Potential delay if late | Procurement | Owner | Medium | Conditional | Moderate | Confirm and deliver third steel order
BD-CW-SAMCO-ACE-LET-STR-043 | 12-Jan-2026 | Weather Notice | Suspension of Tower Crane Operations | Notify crane suspension due high winds | Resume crane operation when weather permits | No scope impact | Weather / SAMCO safety decision | Tower crane lifting operations | Safe wind conditions | Low to Medium | Minor productivity impact | Weather / Safety | Shared / Weather | Low | Low / Conditional | Weak | Record suspension and resume safely
BD-CW-SAMCO-ACE-LET-STR-044 | 15-Jan-2026 | Procurement Delay Notice | Delay in Supplying Reinforcement Steel | Notify owner steel supply delay and reserve rights | Expedite steel supply, acknowledge EOT rights, note SAMCO supplied 120 tons | No scope change; material supply delay | Owner for steel supply; SAMCO mitigation | Reinforcement fabrication/installation | Owner-supplied steel under advance payment arrangement | High | Potential EOT, cost recovery/self-procurement | Procurement / Delay | Owner | High | Moderate to High | Moderate to Strong | Expedite supply and certify mitigation steel
BD-CW-SAMCO-ACE-LET-STR-045 | 22-Jan-2026 | Commercial Submission | Guarantee Cheque for Reinforcement Steel | Record submission of guarantee cheque for remaining owner steel | Acknowledge cheque receipt and proceed with steel supply | No scope impact | SAMCO / Owner finance | Steel supply guarantee, procurement | Guarantee cheque receipt | Low direct; supports steel delivery | EGP 43.75m guarantee linked to steel supply | Commercial / Procurement | Shared | Low |  |  | Confirm receipt and release remaining steel
BD-CW-SAMCO-ACE-LET-STR-046 | 24-Jan-2026 | Payment Submission | Submission of Interim Payment Certificate No. 3 | Submit IPC No. 3 for review and approval | Review and approve IPC 3 | No scope impact | Engineer / Employer | Payment certification | IPC submission | Low schedule, cash-flow impact | Payment due under contract | Commercial / Payment | Employer / Engineer | Low | Conditional |  | Certify and pay IPC 3
BD-CW-SAMCO-ACE-LET-STR-047 | 24-Jan-2026 | MOM Correction / Commercial Record | Additions to MOM - Coordination Meeting 19-Jan-2026 | Request omitted meeting agreements be added to MOM | Add design review code basis, VO/VAT method, bank guarantee and performance security deletion | No physical scope; commercial/contract administration impact | Shared / Employer / Engineer | Design review, VO valuation, IPC retention/security | Accurate agreed MOM record | Medium | Affects VO valuation and payment deductions | Contract Administration / Commercial | Shared | Low to Medium | Conditional | Moderate | Revise MOM and confirm agreed commercial points
BD-CW-SAMCO-ACE-LET-STR-048 | 26-Jan-2026 | Procurement Delay Notice | Follow-up on Delay of Reinforcement Steel Delivery | Warn steel nearly exhausted and works may suspend | Deliver delayed 26-Nov steel order immediately; reserve EOT rights | No scope change; material shortage affects works | Owner for steel supply | Steel fabrication and structural works | Steel delivery before stock depletion | High | Potential work suspension and EOT/cost | Procurement / Delay | Owner | High | High | Moderate to Strong | Deliver outstanding steel urgently
BD-CW-SAMCO-ACE-LET-STR-049 | 29-Jan-2026 | Response / Conditional Acceptance | Response to LET-025 First Fix MEP Works | Accept first-fix MEP only subject to formal VO/procedure | Issue VO, share BOQ or allow SAMCO to prepare BOQ, approve proposal | Adds first-fix MEP/interface works as variation | Engineer/Employer for VO; SAMCO if instructed | MEP first fix, drawings review, concrete interfaces | Formal VI/VO and approved BOQ/proposal | High if not instructed | Variation payment and time implications | Variation / MEP Interface | Shared / Employer | High | Moderate | Moderate | Issue VO/BOQ and process proposal under Clause 13.3
BD-CW-SAMCO-ACE-LET-STR-050 | 03-Feb-2026 | Notice of Variation | Concrete Strength/Cement Content Difference | Notify discrepancy between BOQ and approved structural drawings | Approve cost variation for 300/300 to 350/350 concrete change | Increased concrete strength/cement content for structural frame | Engineer/Designer for instruction; SAMCO for execution | Columns, slabs, beams, shear walls, stairs | PCO RFI instruction and approved drawings | Medium | Additional concrete cost | Variation / Quantity/Specification | Employer / Engineer | Medium | Low to Moderate | Strong | Review and approve cost variation
BD-CW-SAMCO-ACE-LET-STR-051 | 07-Feb-2026 | Procurement Delay / EOT Notice | Reinforcement Steel Supply Status and EOT Entitlement | Notify depletion and non-delivery of second/third steel orders | Expedite owner steel, acknowledge EOT and consequences, note SAMCO supplied 300 tons | No scope change; material supply delay | Owner for steel; SAMCO mitigation | Reinforcement works and fabrication | Owner delivery of second and third orders | High | Potential EOT, cost and disruption | Procurement / Delay | Owner | High | High | Moderate to Strong | Deliver pending steel and record mitigation quantities
BD-CW-SAMCO-ACE-LET-STR-052 | 16-Feb-2026 | Status Update / Reservation | Project Status Update - Buildings B1 to B17 | Update progress and record unresolved design/MEP/steel/BOQ/soil issues | Issue pending instructions, drawings, BOQ, soil feedback and steel supply | No direct scope; multiple blockers identified | Shared / Employer | B1-B17, tank, raft, columns, steel, MEP, soil | Pending approvals, steel deliveries, design review, soil results | High | Potential cumulative delay/cost if unresolved | Progress / Interface / Procurement | Shared / Owner | High | Conditional High | Moderate | Resolve listed blockers and update schedule
BD-CW-SAMCO-ACE-LET-STR-053 | 24-Feb-2026 | Procurement Delay / Commercial Claim Reservation | Reinforcement Steel Order No. 2 Delay | Record late/irregular supply and request revised distribution/payment | Expedite outstanding quantities, approve diameter redistribution, certify/pay SAMCO-procured steel | No scope change; procurement sequence modified | Owner for supply; SAMCO mitigation | Reinforcement order 2, fabrication, structural works | Approval and delivery of adjusted steel order | High | Payment for self-procured steel and possible EOT/cost | Procurement / Commercial | Owner | High | High | Strong | Approve redistribution, deliver steel, certify SAMCO material
BD-CW-SAMCO-ACE-LET-STR-054 | 24-Feb-2026 | Payment Delay Notice | IPC Payment Status | Notify late IPC payment and reserve delay interest/EOT/cost rights | Confirm payment timeline for outstanding IPCs | No scope impact but cash-flow risk | Employer / Engineer | IPC 1, IPC 2, IPC 3 payments | Contractual 45-day payment period | Medium through cash flow | Delay interest and possible finance/prolongation claim | Commercial / Payment | Employer | Medium | Conditional | Moderate | Confirm/pay outstanding IPCs and interest if due
BD-CW-SAMCO-ACE-LET-STR-055 | 24-Feb-2026 | Payment Record | Actual Receipt Date of Cheque - IPC 1 | Record actual cheque receipt date for IPC 1 | Use 10-Feb-2026 as actual receipt date for payment period | No scope impact | Employer / SAMCO | IPC 1 payment record | Cheque physical receipt | Low | Affects delay interest calculation | Commercial / Payment | Employer | Low |  | Moderate | Record actual payment receipt date
BD-CW-SAMCO-ACE-LET-STR-056 | 25-Feb-2026 | Payment Submission | Submission of Interim Payment Certificate No. 4 | Submit IPC No. 4 for review and approval | Review and approve IPC 4 | No scope impact | Engineer / Employer | Payment certification | IPC submission | Low schedule, cash-flow impact | Payment due under contract | Commercial / Payment | Employer / Engineer | Low | Conditional |  | Certify and pay IPC 4
BD-CW-SAMCO-ACE-LET-STR-057 | 11-Mar-2026 | Delay Notice / Design Information | Delayed Technical Responses and Outstanding Coordinated Drawings | Notify missing coordinated drawings and delayed RFI responses may affect future works | Issue final coordinated drawings and respond to RFIs/technical conflicts | Potential design coordination impacts | Engineer / Employer / Consultant | Tank raft, MEP/structural/architectural coordination, future activities | Final coordinated drawings and RFI responses | High | Potential EOT/cost from delayed information | Design Information / Interface | Engineer / Employer | High | High | Strong | Issue RFI responses and coordinated drawings urgently
BD-CW-SAMCO-ACE-LET-STR-058 | 14-Mar-2026 | Weather Notice | Work Suspension Due to Severe Weather | Notify temporary suspension from strong winds/dust | Record weather suspension; resume next day | No scope impact | Weather / SAMCO safety decision | General site works | Safe weather conditions | Low | Minor productivity impact | Weather / Safety | Weather | Low | Low / Conditional | Weak | Record event and resume works
BD-CW-SAMCO-ACE-LET-STR-059 | 25-Mar-2026 | Payment Submission | Submission of Interim Payment Certificate No. 5 | Submit IPC No. 5 for review and approval | Review and approve IPC 5 | No scope impact | Engineer / Employer | Payment certification | IPC submission | Low schedule, cash-flow impact | Payment due under contract | Commercial / Payment | Employer / Engineer | Low | Conditional |  | Certify and pay IPC 5
BD-CW-SAMCO-ACE-LET-STR-060 | 25-Mar-2026 | Weather Notice | Work Interruption Due to Adverse Weather | Notify interruption from heavy rainfall 25-26 Mar | Record interruption; resume 28-Mar | No scope impact | Weather / SAMCO safety decision | General site works | Weather improvement | Low to Medium | Minor to moderate productivity impact | Weather / Delay | Weather | Medium | Conditional | Weak to Moderate | Record event and update weather log
BD-CW-SAMCO-ACE-LET-STR-061 | 29-Mar-2026 | Weather Notice | Work Interruption Due to Adverse Weather | Notify workforce could not attend due heavy rainfall | Record interruption; resume 30-Mar | No scope impact | Weather / SAMCO workforce | Steel fixing, carpentry, general site works | Weather improvement and workforce return | Low to Medium | Productivity loss | Weather / Delay | Weather | Medium | Conditional | Weak to Moderate | Record event and update schedule impact if any
BD-CW-SAMCO-ACE-LET-STR-062 | 31-Mar-2026 | Procurement Delay Notice | Follow-up on Reinforcement Steel Delivery | Notify order 2 partly delivered and order 3 outstanding | Urgently expedite pending steel; reserve EOT/cost; record SAMCO supplied over 420 tons | No scope change; material supply delay | Owner for steel; SAMCO mitigation | Reinforcement works | Full delivery of second and third steel orders | High | Potential EOT/cost and mitigation payment | Procurement / Delay | Owner | High | High | Strong | Deliver steel and certify mitigation material
BD-CW-SAMCO-ACE-LET-STR-063 | 31-Mar-2026 | Design Change Notice | Comparison of Design Issued 18-Mar-2026 vs 27-Oct-2025 | Identify discrepancies after works already executed under prior approved design | Maintain approved executed works and issue clear coordinated revisions | Potential redesign/rework risk | Employer/Designer/Engineer | Foundations, columns, retaining walls, slabs, stairs/cores | Decision on new design vs executed approved works | High | Potential rework, delay and cost | Design Change / Rework | Employer / Designer | High | High | Strong | Issue coordinated revision clouded drawings and direction on executed works
BD-CW-SAMCO-ACE-LET-STR-064 | 02-Apr-2026 | Notice of Claim | Delay in Technical Clarifications | Notify RFI delays are halting water tank/sump/electrical/stair activities | Respond urgently to RFIs 3,4,5,6; acknowledge time/cost claim rights | No scope change; information delay blocks works | Engineer / Consultant | Water tank, basement sumps, electrical works, staircases | RFI responses | High | EOT and cost claim reserved | Design Information / Delay | Engineer / Consultant | High | High | Strong | Issue RFI responses and assess time/cost impact
BD-CW-SAMCO-ACE-LET-STR-065 | 02-Apr-2026 | Weather Notice | Work Interruption Due to Adverse Weather | Notify workforce interruption from rainfall | Record interruption; resume 04-Apr | No scope impact | Weather / SAMCO workforce | Steel fixing, carpentry, general site works | Weather improvement and workforce return | Low to Medium | Productivity loss | Weather / Delay | Weather | Medium | Conditional | Weak to Moderate | Record event and update schedule impact if any
BD-CW-SAMCO-ACE-LET-STR-066 | 11-Apr-2026 | Notice of Claim | Modifications Included in Latest Design Package | Notify RFI 16 delay prevents column activities despite mobilized resources | Respond urgently to RFI 16; reserve time/cost for idle/manpower impact | Potential design modification impact | Engineer / Consultant / Designer | Columns in B1-B4, carpentry and steel works | RFI 16 response/design decision | High | Potential idle resources, EOT and cost | Design Information / Delay | Engineer / Consultant | High | High | Strong | Issue RFI 16 response and coordinate latest design
BD-CW-SAMCO-ACE-LET-STR-067 | 16-Apr-2026 | Notice of Claim | Design Discrepancies and Impact on Time and Cost | Notify conflicting October 2025 and March 2026 structural packages make execution unfeasible | Issue one complete coordinated structural package; reserve EOT and all costs/losses | Potential redesign/rework and work suspension | Employer/Designer/Engineer | Columns, slabs, beams, shop drawings, structural package | Final coordinated structural package and RFI 17 response | High critical sequence impact | EOT, cost, loss/expense claim reserved | Design Discrepancy / Suspension | Employer / Designer | High | High | Strong | Issue single coordinated package and instruction to resume
BD-CW-SAMCO-ACE-LET-STR-068 | 16-Apr-2026 | Payment Delay Notice | Follow-up on Settlement of IPCs | Record late/outstanding IPC payments and reserve financial rights | Confirm payment timeline, pay outstanding IPCs, apply interest where due | No scope impact but cash-flow risk | Employer / Engineer | IPC 1-5 settlement | Contractual payment periods | Medium to High via cash flow | Delay interest, EOT/cost rights reserved | Commercial / Payment | Employer | Medium | Conditional | Moderate to Strong | Confirm/pay IPCs and address interest entitlement
BD-CW-SAMCO-ACE-LET-STR-069 | 19-Apr-2026 | Procurement Delay / Cumulative Impact Notice | Follow-up on Reinforcement Steel Supply and Cumulative Project Impact | Record cumulative owner steel delay and mitigation by SAMCO | Expedite remaining steel; acknowledge EOT, associated costs and contractual entitlements | No scope change; procurement delay affecting sequence | Owner for steel; SAMCO mitigation | Reinforcement supply, fabrication, critical structural works | Full delivery of order 2 balance and order 3 | High | EOT and cost from self-procurement/prolongation | Procurement / Delay | Owner | High | High | Strong | Deliver remaining steel, certify mitigation, assess cumulative delay
BD-CW-SAMCO-ACE-LET-STR-070 | 25-Apr-2026 | Payment Submission | Submission of Interim Payment Certificate No. 6 | Submit IPC No. 6 for review and approval | Review and approve IPC 6 | No scope impact | Engineer / Employer for certification/payment | Payment certification | IPC submission | Low schedule, cash-flow impact | Payment due under contract | Commercial / Payment | Employer / Engineer | Low | Conditional |  | Certify and pay IPC 6
BD-CW-SAMCO-ACE-LET-STR-071 | 27-Apr-2026 | Early Warning / Notice under Sub-Clause 20.1 | Early Warning & Notification of Fact (pursuant to Sub-Clause 20.1) – Site Progress and Constraints for Buildings B1-B4 | Notify the Engineer of site progress constraints and preserve contractual entitlement | Immediate response to RFI No. 17; issue updated/complete structural design package; complete outstanding Employer-supplied reinforcement steel deliveries; confirm clarification to permit slab works | Yes – structural works are affected by design discrepancies and material non-availability | Employer (steel supply) / Engineer (design clarification) | Excavation/backfilling continuity; foundation completion; waterproofing; concrete columns; retaining walls; water tank works; slab works for Building B3; reinforcement steel-dependent structural activities | Slab works awaiting RFI response and updated design; reinforcement steel-dependent works awaiting full Employer supply | Out-of-sequence execution; slab works suspended pending clarification; structural package changed in March 2026 versus previously approved shop drawings | Additional cost exposure for contractor-procured steel (>500 tons); productivity loss; prolongation risk; possible disruption to sequence-driven execution | Supply chain / Design coordination / Contractual entitlement | Employer / Engineer | High | High | Strong | Expedite RFI response; issue updated design; deliver pending steel; assess critical path and delay impact; preserve records for claim substantiation
BD-CW-SAMCO-ACE-LET-STR-072 | 27-Apr-2026 | Submission / Meeting Minutes | Submission of Minutes of Meetings - MEP Works (First Fix). | Submit MEP first-fix meeting minutes and preserve rights over missing information and design conflicts | Take note of the MOMs and issue any missing information / clarifications required for execution | First-fix MEP works prior to concrete casting | Engineer / Design parties for information; SAMCO for execution only | MEP first fix, embedded items, concrete casting interfaces | Approved drawings and coordinated details before casting | Design conflicts and missing details can block first-fix execution and concrete casting sequence | Potential time and cost consequences expressly reserved | Interface / Design coordination | Engineer / Employer | High | Moderate | Moderate to Strong | Confirm MOM instructions, close design conflicts, and issue clarifications before casting
BD-CW-SAMCO-ACE-LET-STR-073 | 28-Apr-2026 | Clarification / Technical Notice | Scope Clarification - Internal Tank Waterproofing. | Request clarification on internal tank waterproofing scope and execution arrangement | Confirm status, responsible scope, and final execution arrangement for internal waterproofing | Potential interface between structural scope, architectural scope, and internal tank waterproofing system | Engineer / Employer clarification on final scope | Water tank internal waterproofing, repair / injection sequence, final lining works | Architectural package issuance and Engineer instruction | Unclear waterproofing scope can delay the final tank execution sequence | Potential variation, warranty, and scope implications | Technical / Scope clarification | Engineer / Employer | Medium | Conditional | Moderate | Issue formal clarification on waterproofing scope and execution arrangement
BD-CW-SAMCO-ACE-LET-STR-074 | 29-Apr-2026 | Response / Reporting Compliance | Re: Non-Compliance with Submission of Weekly Progress Reports. | Respond to weekly reporting non-compliance notice and confirm recovery submissions | Allow one week to submit backlog and align a unified reporting format | No scope impact; controls and reporting compliance | SAMCO for reporting; project-framework alignment is shared | Weekly reporting, baseline monitoring, progress documentation | Stable agreed reporting format and project phasing context | No direct physical delay, but contractual administration and reporting visibility are affected | Possible withholding / compliance exposure if unresolved | Controls / Contract compliance | SAMCO / Shared | Medium | Low | Weak to Moderate | Submit outstanding weekly reports and agree a unified reporting template
BD-CW-SAMCO-ACE-LET-STR-075 | 30-Apr-2026 | Commercial Response / Reservation | Re: BD-ACEPM-SAMCO-LET-031 | Respond to IPC settlement clarification and reserve rights due to project constraints | Continue timely certification and payment of IPCs under the Contract | No scope impact but payment administration is affected by project constraints | Employer / Engineer for certification and payment; external constraints affecting progress are beyond SAMCO control | IPCs, valuation of executed works, commercial administration | Certification cycle and removal of steel/design/approval constraints | Reduced progress and valuation because of employer / engineer-driven constraints | Cash-flow exposure and reserved EOT / cost entitlement | Commercial / Payment | Employer / Engineer | Medium | Conditional | Moderate | Facilitate certification / payment and address the delaying constraints
BD-CW-SAMCO-ACE-LET-STR-076 | 09-May-2026 | Notice of Claim / Design Discrepancy | Notice of Claim - Impact of Revised Structural Drawings on Project Progress [Sub-Clause 1.9 / 8.4 / 20.1] | Notify a claim for delay caused by revised structural packages and conflicting instructions | Acknowledge the delay event and assess EOT / cost implications | Columns, shuttering, slabs, shop drawings, and construction sequence | Engineer / Employer design management | Columns, shuttering, slab elements, shop drawing development | Final coordinated structural package and consistent instructions | Works were suspended from 24-Mar-2026 until 30-Apr-2026 and the critical path was disrupted | Direct and indirect cost claim; prolongation exposure | Design coordination / Claim | Engineer / Employer | High | High | Strong | Recognize the hold period, issue a clear coordinated design basis, and assess the claim
BD-CW-SAMCO-ACE-LET-STR-077 | 11-May-2026 | Variation Notice / Reservation of Rights | Notice of Variation and Reservation of Rights - Backfilling Works Behind Retaining Wall. | Treat retaining-wall backfilling as a variation and preserve time / cost entitlement | Issue a Variation Order covering cost, time, and measurement procedure | Additional backfilling methodology beyond original BOQ scope | Employer / Engineer to issue VO and confirm valuation route | Retaining wall backfilling and dependent structural / earthworks activities | Variation Order or written instruction | Delay in VO / instruction can affect execution and the critical path | Direct cost, overhead / profit, prolongation, and measurement entitlement | Variation / Commercial | Employer / Engineer | High | High | Strong | Issue the VO or written instruction and confirm valuation / time treatment
BD-CW-SAMCO-ACE-LET-STR-078 | 11-May-2026 | Meeting Minutes Submission | Submission of MOM - Site Meeting for Mechanical Works (First Fix) Held on Wednesday 06/05/2026. | Submit first-fix MEP site meeting minutes for record | Review the MOM and issue comments or amendments if any | MEP first-fix coordination and execution records | Shared coordination between SAMCO, Engineer, and MEP stakeholders | First-fix mechanical works and related coordination items | Site coordination decisions and recorded action closure | Unresolved coordination items can delay first-fix and related civil sequencing | Potential indirect time / coordination consequences | Coordination / Interface | Shared | Medium | Conditional | Moderate | Close the MOM action items and confirm the first-fix coordination route
BD-CW-SAMCO-ACE-LET-STR-079 | 24-May-2026 | Procurement Delay / EOT Response | Reply to Notification of Reinforcement Steel Supply Status and Entitlement to Time Extensions | Rebut the steel supply status notice and confirm delayed employer steel caused actual delay | Acknowledge the time impact and confirm the status of outstanding steel supply | No scope change; employer free-issue steel delivery affected execution sequence | Employer / Client steel supply | Reinforcement works and steel-dependent structural activities | Full and timely delivery of steel batches | Delayed second batch and revised third batch requirements disrupted the planned construction sequence | Time-impact claim and mitigation cost exposure | Procurement / Delay | Employer | High | High | Strong | Finalize third-batch details, confirm prior supplies, and assess the time impact
BD-CW-SAMCO-ACE-LET-STR-080 | 24-May-2026 | Delay Notice Response / Reservation | Response to Notice - Alleged Failure to Achieve Section (1) Milestone | Respond to the milestone-failure notice and explain the combined steel, IFC, and RFI impacts | Assess the milestone position in the proper contractual context and accept a revised plan | Section (1) milestone and critical structural activities | Employer (steel) / Engineer (IFC and RFI response) | Steel-dependent critical activities, suspended IFC-affected works, Section (1) milestone | Timely steel supply, resolved IFC conflicts, and timely RFI responses | Progress was disrupted from 18-Mar-2026 and milestone recovery now depends on the revised plan | Potential EOT and claim rights expressly preserved | Schedule / Design / Supply | Employer / Engineer | High | High | Strong | Assess impacted activities, review the revised plan, and evaluate entitlement
BD-CW-SAMCO-ACE-LET-STR-081 | 24-May-2026 | Payment Submission | Submission of Interim Payment Certificate No. 7 | Submit IPC No. 7 for review and approval | Review and approve IPC 7 | No scope impact | Engineer / Employer for certification/payment | Payment certification | IPC submission | Low schedule, cash-flow impact | Payment due under contract | Commercial / Payment | Employer / Engineer | Low | Conditional |  | Certify and pay IPC 7
BD-CW-SAMCO-ACE-LET-STR-082 | 25-May-2026 | Clarification / Claim Notice | Clarification on Internal Waterproofing System, Execution Sequence and Performance Warranty - Water Tank. | Clarify the water-tank waterproofing system and reserve claim rights over delayed instruction | Confirm the final approved waterproofing system and responsible executing party | Tank waterproofing, repair / injection sequence, and warranty responsibility | Engineer / Employer / architectural scope clarification | Water tank repair works, internal waterproofing, and warranty completion path | Engineer clarification, approved system, and coordinated architectural information | Tank works sequence and warranty path remain blocked without final instruction | Potential additional cost and EOT claim due to delayed clarification | Technical / Contractual entitlement | Engineer / Employer | High | High | Moderate to Strong | Issue the final instruction on the waterproofing system and assess entitlement effects

## From ACE to SAMCO
Ref No | Date | Type | Subject | Main Purpose | Key Requests | Scope Impact | Responsibility | Affected Activities | Start Dependency | Sequence Impact | Commercial Impact | Risk Type | Risk Owner | Delay Risk | EOT Potential | Claim Strength | Required Actions
BD-ACEPM-SAMCO-LET-001 | 24-Jun-2025 | Notice | Outstanding Deliverables | Record overdue deliverables | Submit crane, program, CV, methodology, soil report, steel data | No new scope | Contractor | Cranes, soil replacement, shop drawings, steel | Crane/docs before soil works | High | Possible delay damages | Schedule/contract | Contractor | High | Low | Contractor weak | Submit all overdue items
BD-ACEPM-SAMCO-LET-002 | 25-Jun-2025 | Delay notice | Tower Crane No. 1 delay | Warn crane delay affects soil works | Start TC1 installation and confirm date | No new scope | Contractor | TC1, soil replacement | TC1 needed before soil stage | High | Contractor delay exposure | Schedule | Contractor | High | Low | Contractor weak | Install TC1 immediately
BD-ACEPM-SAMCO-LET-003 | 31-Aug-2025 | Clarification | Survey and batching plant | Respond to survey, ramp, batching plant issues | Follow consultant review; finalize plant/ramp position | Possible interface impact | Shared | Boundaries, ramp, plant, Zone 2 | Zone 2 after full handover | Medium | Possible relocation cost/time if owner-caused | Interface/site | Shared | Medium | Conditional | Moderate if owner-caused | Close reviews and approvals
BD-ACEPM-SAMCO-LET-004 | 17-Sep-2025 | Submission notice | Required contractual submissions | Enforce pre-construction submissions | Staff, program, HSE, QA, BBS, reports | No new scope | Contractor | Mobilization, procurement, reporting | Submissions before proper progress | Medium | Procurement/payment risk | Contract/schedule | Contractor | High | Low | Contractor weak | Submit full package
BD-ACEPM-SAMCO-LET-005 | 17-Sep-2025 | Response | Site obstacles B1-B4 | Rebut handover/leakage delay claim | Follow claim procedure; submit program | No change; events closed | Contractor | Handover, tests, leakage, program | Commencement fixed 11-Sep-2025 | Low/Medium | No EOT recognized | Contract/site | Contractor | Low | Low | Contractor weak | Submit compliant claim if any
BD-ACEPM-SAMCO-LET-006 | 22-Sep-2025 | Reminder | Design verification | Enforce design verification duty | Submit consultant prequalification and report | No new scope | Contractor | Design review | Consultant approval before review | Medium | Contractor own cost | Technical/contract | Contractor | Medium | Low | Contractor weak | Submit prequalification/report
BD-ACEPM-SAMCO-LET-007 | 22-Sep-2025 | Rejection | Insurance policy | Reject incomplete insurance | Resubmit all required policies by 08-Oct | No new scope | Contractor | Insurance, site equipment | Valid insurance for site operations | Low/Medium | Uninsured equipment may be barred | Insurance/contract | Contractor | Medium | Low | Contractor weak | Resubmit complete policies
BD-ACEPM-SAMCO-LET-008 | 28-Sep-2025 | Claim rejection | Site ramp works | Reject cost/EOT for ramp | Maintain/modify access route at own cost | Within contractor scope | Contractor | Ramp, access, deliveries | Access route by contractor | Medium | No payment or EOT | Access/commercial | Contractor | Medium |  | Contractor weak | Maintain ramp and proceed
BD-ACEPM-SAMCO-LET-009 | 28-Sep-2025 | Access clarification | Borehole locations | Clarify boreholes outside handed site | Complete access/procedure before works | Outside handed area | Shared | Confirmatory boreholes | Site possession/permissions | Low/Medium | No direct impact | Access/permit | Shared | Low | Conditional | Moderate if owner blocks access | Formalize approvals
BD-ACEPM-SAMCO-LET-010 | 02-Oct-2025 | Submittal rejection | Consultant CV/design review | Reject proposed consultant CV | Submit 3 accredited consultant firms | No new scope | Contractor | Design review consultant | Approval before design review | Medium | Contractor delay risk | Technical/contract | Contractor | Medium | Low | Contractor weak | Resubmit consultant package
BD-ACEPM-SAMCO-LET-011 | 04-Oct-2025 | Response/instruction | Pipe breakage/excavation | Close leakage issue; instruct rectification | Proceed with corrective works | Corrective works area | Contractor | Excavation, B5/B6/B14/B15 area | Leak already repaired | Medium | No time/cost admitted | Site/technical | Contractor/shared | Low/Medium | Low | Contractor weak | Execute rectification
BD-ACEPM-SAMCO-LET-012 | 05-Oct-2025 | Procedure notice | Variation procedure | Remind 14-day notice rule | Submit notices for scope/time/cost impact | Procedure only | Contractor | All potential variations | Notice after instruction | Low direct | Preserves/limits entitlement | Contract/commercial | Contractor | Low | Conditional | Depends on compliance | Follow 13.3 notice process
BD-ACEPM-SAMCO-LET-013 | 05-Oct-2025 | Technical instruction | Soil replacement recommendation | Instruct per Civitech comments | Follow geotechnical recommendations | Technical clarification | Contractor/Civitech | Ground tank foundation, soil tests | Civitech approval/comments | Medium | No determination | Geotechnical | Shared | Medium | Conditional | Moderate if scope changes | Implement comments
BD-ACEPM-SAMCO-LET-014 | 12-Oct-2025 | Delay notice | Soil replacement B1/B2 | Warn no start after instruction | Start gravel supply, works, tests | No new scope | Contractor | B1/B2 soil replacement | Handover/instruction on 07-Oct | High | Employer reserves claims/damages | Schedule/quality | Contractor | High | Low | Employer strong | Mobilize and test
BD-ACEPM-SAMCO-LET-015 | 15-Oct-2025 | Response | Delay of works at site | Rebut contractor delay position | Start B3/B4; continue supply/access duties | B1/B2 by Employer; B3/B4 by Contractor | Contractor | Earthworks, soil supply, access | B3/B4 handed 07-Sep | High | Contractor bears supply/access risk | Schedule/contract | Contractor | High | Low | Contractor weak | Proceed and maintain access
BD-ACEPM-SAMCO-LET-016 | 20-Oct-2025 | Coordination response | Reinforcement steel quantity | Clarify first steel requisition priority | Proceed with prioritized quantities | No scope change | Shared | Steel first delivery | Contractor requisition | Medium | Supply coordination risk | Procurement | Shared | Medium | Conditional | Moderate if owner delay proven | Confirm quantities/delivery
BD-ACEPM-SAMCO-LET-017 | 26-Nov-2025 | Variation enforcement | VI-0003 rejection | Reject refusal of variation | Execute VI immediately | Variation/interface works affirmed | Contractor | MEP/interface/enabling works | VI under 13.1/13.3 | High | Remedies/delay damages reserved | Contract/schedule | Contractor | High | Low | Employer strong | Execute VI; submit proposal
BD-ACEPM-SAMCO-LET-018 | 03-Dec-2025 | Non-compliance notice | Programme delay | Record missing revised program | Submit revised program addressing comments | No new scope | Contractor | Project program, monitoring | Approved program needed | High | Possible 8.6/8.7 actions | Schedule/contract | Contractor | High | Low | Contractor weak | Resubmit program
BD-ACEPM-SAMCO-LET-019 | 04-Dec-2025 | Variation rebuttal | GWT flanges | Reject refusal of VI Ref. 4 | Execute supply/install flanges | Variation scope affirmed | Contractor | Ground water tank flanges | Binding VI unless goods unavailable | High | Remedies reserved | Contract/technical | Contractor | High | Low | Employer strong | Execute works
BD-ACEPM-SAMCO-LET-020 | 08-Dec-2025 | Delay notice | Design review | Demand full design review | Submit comprehensive report for all works | No design change instructed | Contractor | Structural design review | Due before 11-Nov | High | May lose EOT/cost entitlement | Technical/schedule | Contractor | High | Low | Contractor weak | Issue full report
BD-ACEPM-SAMCO-LET-021 | 10-Dec-2025 | Reporting notice | Periodic reports delay | Record missing weekly/monthly reports | Submit overdue reports | No scope impact | Contractor | Reports, logs, IPC support | From commencement/monthly cycle | Medium | IPC withholding possible | Controls/commercial | Contractor | Medium | Low | Contractor weak | Submit reports
BD-ACEPM-SAMCO-LET-022 | 28-Dec-2025 | Design clarification | Design review | Respond to limited B1/B2 review | Complete review for all buildings/elements | No relief; criteria clarified | Contractor | B1-B4, foundations, slabs, systems | Review all works under 4.1 | High | No liability relief | Technical/contract | Contractor | High | Conditional low | Weak/uncertain | Submit remaining feedback
BD-ACEPM-SAMCO-LET-023 | 11-Jan-2026 | Incident closure | Water pipeline leakage | Confirm leak resolved/no impact | None beyond monitoring | No scope impact | Employer handled support | Utility protection, nearby works | Incident closed 01-Jan | Low | No cost/time accepted | Site condition | Closed | Low |  | Contractor weak | Monitor pipe supports
BD-ACEPM-SAMCO-LET-024 | 22-Jan-2026 | Criteria clarification | Adopted design criteria | Confirm seismic criteria/IF 1.0 | Proceed with review using clarified criteria | No scope change | Contractor | Structural design review | Use Employer criteria | Medium/High | No waiver/relief | Technical/contract | Contractor | Medium | Low | Contractor weak | Continue verification
BD-ACEPM-SAMCO-LET-025 | 27-Jan-2026 | Contract interpretation | MEP first fix variation | Confirm first fix works are required | Execute unless goods unavailable notice | Variation/necessary works affirmed | Contractor | Sleeves, flange adapters, MEP first fix | No suspension under 13.3 | High | Damages/remedies reserved | Contract/schedule | Contractor | High | Low | Employer strong | Execute variation
BD-ACEPM-SAMCO-LET-026 | 02-Feb-2026 | Variation clarification | Response to LET-025 | Confirm VIs already issued | Execute VIs and submit proposal | Current VIs only; new works need instruction | Contractor | VI-0003/0004, coordination studies | Written instruction for new works | High | Valued through 13.3 proposal | Contract/commercial | Contractor/shared | High | Conditional | Moderate if procedure followed | Execute and submit proposal
BD-ACEPM-SAMCO-LET-027 | 15-Feb-2026 | Commercial notice | Required breakdown delay | Warn missing breakdown affects payments | Submit breakdown within 7 days | No physical scope | Contractor | IPCs, tax/value breakdown, variations | Breakdown for certification | Low direct | IPC deferral/adjustment risk | Commercial/contract | Contractor | Low |  | Contractor weak | Submit breakdown
BD-ACEPM-SAMCO-LET-028 | 16-Feb-2026 | EOT rebuttal | Steel supply status | Confirm steel delivered; require mitigation | Plan resources, sequence, submit mitigation | No scope change | Contractor | Reinforcement works | Steel delivered; contractor planning | High | Delay damages reserved | Procurement/schedule | Contractor | High | Low/conditional | Weak to moderate | Submit mitigation plan
BD-ACEPM-SAMCO-LET-029 | 24-Feb-2026 | Protocol notice | Project status update | Reject routine status letters as contractual basis | Use reports/meetings or proper notices | No scope impact | Contractor | B1-B17 status reporting | Approved channels | Low | No waiver/recognition | Contract/admin | Contractor | Low |  | Contractor weak | Use correct channels
BD-ACEPM-SAMCO-LET-030 | 15-Mar-2026 | Report comments | February 2026 MPR | Comment on incomplete monthly report | Revise report with milestones, logs, SPI, VO status | No scope impact | Contractor | Monthly reporting, controls | Due monthly; comply GR 8.3 | Medium | Issues not entitlement; claims under 20.1 | Controls/commercial | Contractor | Medium | Low | Contractor weak | Revise/resubmit MPR
BD-ACEPM-SAMCO-LET-031 | 19-Apr-2026 | Payment clarification | IPC settlement follow-up | Reject overdue payment allegation | Comply with IPC threshold/monthly cycle | No scope impact | Contractor | IPCs 1-3, payment certification | IPC must meet 70% monthly cash flow | Low | Admin payments not waiver | Commercial/contract | Contractor | Low |  | Contractor weak | Submit compliant IPCs
BD-ACEPM-SAMCO-LET-033 | 05-May-2026 | Contractual Response / Rejection | Re: Early Warning & Notification of Fact (pursuant to Sub-Clause 20.1) – Site Progress and Constraints for Buildings B1–B4 | Reject the contractor's notice as a valid Sub-Clause 20.1 claim and require compliance with formal notice/claim procedure | Submit a fully detailed claim within 42 days; provide clear substantiation of the event and its effects; follow the contract communication protocol for valid contractual notices | No direct scope variation acknowledged | Contractor (for procedural compliance) | Claim administration / notice compliance rather than works execution | Valid notice and detailed claim submission under Sub-Clause 20.1 | No recognition of entitlement from the referenced correspondence; the Engineer treats the submission as a general narrative rather than a valid claim | No commercial entitlement acknowledged; rights expressly reserved by Employer and Engineer | Procedural / contractual compliance | Contractor | Medium | Low / Conditional | Contractor weak | Resubmit a properly substantiated claim/notice in strict compliance with the Contract; attach supporting records and formal causal linkage
BD-ACEPM-SAMCO-LET-034 | 06-May-2026 | Commercial Compliance / Deduction Notice | Submission of proof of payment for engineering stamps due on contractual works. | Require official proof of engineering-stamp payment and reserve deduction from upcoming payments if proof is not submitted. | Submit official approved documents and receipts proving payment of engineering stamps before approval of the next payment certificate. | No scope change | Contractor | Payment certification / engineering-stamp compliance |  | Low | Possible deduction / withholding from upcoming payments | Commercial / compliance | Contractor | Low | Low | Employer strong | Submit engineering-stamp payment proof and receipts immediately
BD-ACEPM-SAMCO-LET-035 | 11-May-2026 | EOT rebuttal / steel supply position | Re: Notification of Reinforcement Steel Supply Status and Entitlement to Time Extensions | Reject the contractor's steel time-extension position, confirm the final remaining steel batch was delivered, and require mitigation to maintain completion. | Proceed diligently, mitigate any delay effects, maintain the Time for Completion, and submit a mitigation plan. | No scope change | Contractor | Reinforcement works and steel-dependent structural activities | Usable steel delivery and contractor mitigation planning | High | No entitlement acknowledged; rights expressly reserved | Procurement / schedule | Contractor | High | Low / Conditional | Contractor weak | Submit mitigation plan and maintain progress despite delivered steel
BD-ACEPM-SAMCO-LET-036 | 11-May-2026 | Delay notice / rate of progress | Failure to Achieve Section (1) Milestone within the Contractual Due Date | Record failure to achieve the Section (1) milestone and require a recovery plan under the contract. | Submit a detailed recovery plan within 10 days and take immediate actions to expedite the Works. | No scope change | Contractor | Ground floor ceiling slab milestone and dependent critical structural works | Recovery planning and improved rate of progress | High | Possible delay damages and contractual exposure if slippage continues | Schedule / milestone compliance | Contractor | High | Low / Conditional | Contractor weak | Submit recovery plan and accelerate progress immediately
BD-ACEPM-SAMCO-LET-037 | 17-May-2026 | Slow progress notice / monthly report comments | Notice of Slow Progress Rate and Comments on Monthly Progress Report - April 2026 | Record slow progress against the approved programme and require correction of the April monthly report and mitigation measures. | Address all monthly report comments, re-submit the report officially, improve performance, and provide a mitigation / recovery report. | No scope change | Contractor | Critical project activities, progress reporting, and recovery planning | Corrected progress reporting and immediate corrective actions | High | Possible contractor liability for consequences of non-compliance | Schedule / reporting / contractual compliance | Contractor | High | Low / Conditional | Contractor weak | Correct the April report, improve resource allocation, and submit mitigation measures

## SAMCO to ACE Links
Thread | SAMCO Ref No | SAMCO Sheet Row | SAMCO Date | SAMCO Type | SAMCO Subject | Related ACE Ref No(s) | ACE Sheet Row(s) | ACE Date(s) | ACE Subject(s) | Relationship | Confidence | SAMCO Claim Strength | ACE Claim Strength | SAMCO Delay Risk | ACE Delay Risk | Recommended Follow-up
Concrete specification variation | BD-CW-SAMCO-ACE-LET-STR-050 | 51 | 03-Feb-2026 | Notice of Variation | Concrete Strength/Cement Content Difference |  |  |  |  | No direct ACE response in table | Low | Strong |  | Medium |  | Locate Engineer determination/VO response
Contractual submissions | BD-CW-SAMCO-ACE-LET-STR-006 | 7 | 22-Sep-2025 | Response | RE: Response to Letter No. BD-ACEPM-SAMCO-LET-004 | BD-ACEPM-SAMCO-LET-004 | 5 | 17-Sep-2025 | BD-ACEPM-SAMCO-LET-004 - Required contractual submissions | Response to ACE submission notice | High | Weak | Contractor weak | Medium | High | Track remaining submission approvals
Critical MEP interface / tank base slab | BD-CW-SAMCO-ACE-LET-STR-041 | 42 | 06-Jan-2026 | Urgent Notice / Conditional Proposal | Critical Interface Issue on Critical Path | BD-ACEPM-SAMCO-LET-025; BD-ACEPM-SAMCO-LET-026 | 26; 27 | 27-Jan-2026; 02-Feb-2026 | BD-ACEPM-SAMCO-LET-025 - MEP first fix variation ¦ BD-ACEPM-SAMCO-LET-026 - Response to LET-025 | Directly related to MEP first-fix instruction thread | High | Strong if instruction delayed | Employer strong; Moderate if procedure followed | High | High; High | Issue urgent VO, approved drawings and supervision
Delegation / administration | BD-CW-SAMCO-ACE-LET-STR-001 | 2 | 20-May-2025 | Delegation | Delegation of Authority |  |  |  |  | No direct ACE response in table | Low |  |  |  |  | Keep for authority record only
Delegation / administration | BD-CW-SAMCO-ACE-LET-STR-002 | 3 | 30-Jun-2025 | Delegation | Delegation of Authority |  |  |  |  | No direct ACE response in table | Low |  |  |  |  | Keep for authority record only
Design discrepancies / claim | BD-CW-SAMCO-ACE-LET-STR-067 | 68 | 16-Apr-2026 | Notice of Claim | Design Discrepancies and Impact on Time and Cost |  |  |  |  | No direct ACE response in table | Low | Strong |  | High |  | Track pending RFI 17 / coordinated package response
Design discrepancy / revised package | BD-CW-SAMCO-ACE-LET-STR-063 | 64 | 31-Mar-2026 | Design Change Notice | Comparison of Design Issued 18-Mar-2026 vs 27-Oct-2025 | BD-ACEPM-SAMCO-LET-022; BD-ACEPM-SAMCO-LET-024 | 23; 25 | 28-Dec-2025; 22-Jan-2026 | BD-ACEPM-SAMCO-LET-022 - Design review ¦ BD-ACEPM-SAMCO-LET-024 - Adopted design criteria | Same design criteria/review thread | Medium | Strong | Weak/uncertain; Contractor weak | High | High; Medium | Issue coordinated revision decision for executed works
Design modification / RFI 16 delay | BD-CW-SAMCO-ACE-LET-STR-066 | 67 | 11-Apr-2026 | Notice of Claim | Modifications Included in Latest Design Package |  |  |  |  | No direct ACE response in table | Low | Strong |  | High |  | Link to RFI 16 response when available
Design review | BD-CW-SAMCO-ACE-LET-STR-026 | 27 | 30-Nov-2025 | Technical Meeting Request | Reply of Design Review | BD-ACEPM-SAMCO-LET-020; BD-ACEPM-SAMCO-LET-022 | 21; 23 | 08-Dec-2025; 28-Dec-2025 | BD-ACEPM-SAMCO-LET-020 - Design review ¦ BD-ACEPM-SAMCO-LET-022 - Design review | Same design review thread | Medium | Moderate | Contractor weak; Weak/uncertain | High | High; High | Hold/record technical meeting outcomes
Design review | BD-CW-SAMCO-ACE-LET-STR-029 | 30 | 07-Dec-2025 | Design Reservation | Design Review | BD-ACEPM-SAMCO-LET-020 | 21 | 08-Dec-2025 | BD-ACEPM-SAMCO-LET-020 - Design review | Same design review delay thread | High | Moderate | Contractor weak | High | High | Close comments before reinforcement start
Design review / criteria | BD-CW-SAMCO-ACE-LET-STR-030 | 31 | 11-Dec-2025 | Response / Design Reservation | Re: Design Review | BD-ACEPM-SAMCO-LET-020; BD-ACEPM-SAMCO-LET-022; BD-ACEPM-SAMCO-LET-024 | 21; 23; 25 | 08-Dec-2025; 28-Dec-2025; 22-Jan-2026 | BD-ACEPM-SAMCO-LET-020 - Design review ¦ BD-ACEPM-SAMCO-LET-022 - Design review ¦ BD-ACEPM-SAMCO-LET-024 - Adopted design criteria | Response to ACE design review letters and later criteria clarification | High | Moderate to Strong | Contractor weak; Weak/uncertain; Contractor weak | High | High; High; Medium | Confirm final design criteria and review scope
Design review / criteria | BD-CW-SAMCO-ACE-LET-STR-034 | 35 | 17-Dec-2025 | Design Review / Reservation | Re: Design Review | BD-ACEPM-SAMCO-LET-022; BD-ACEPM-SAMCO-LET-024 | 23; 25 | 28-Dec-2025; 22-Jan-2026 | BD-ACEPM-SAMCO-LET-022 - Design review ¦ BD-ACEPM-SAMCO-LET-024 - Adopted design criteria | Directly addressed by ACE design clarification/criteria letters | High | Strong if criteria/design changed | Weak/uncertain; Contractor weak | High | High; Medium | Confirm adopted criteria and designer liability position
Design review / criteria | BD-CW-SAMCO-ACE-LET-STR-040 | 41 | 05-Jan-2026 | Reservation / Design Instruction Request | Continuation of Works and Final Written Instructions | BD-ACEPM-SAMCO-LET-022; BD-ACEPM-SAMCO-LET-024 | 23; 25 | 28-Dec-2025; 22-Jan-2026 | BD-ACEPM-SAMCO-LET-022 - Design review ¦ BD-ACEPM-SAMCO-LET-024 - Adopted design criteria | Same design instruction and criteria thread | High | Strong if later change occurs | Weak/uncertain; Contractor weak | Medium to High | High; Medium | Keep written instruction and rights reservation
Design verification consultant | BD-CW-SAMCO-ACE-LET-STR-009 | 10 | 24-Sep-2025 | Submittal | Submission of Consultant CV and Approval Certificate | BD-ACEPM-SAMCO-LET-006; BD-ACEPM-SAMCO-LET-010 | 7; 11 | 22-Sep-2025; 02-Oct-2025 | BD-ACEPM-SAMCO-LET-006 - Design verification ¦ BD-ACEPM-SAMCO-LET-010 - Consultant CV/design review | Submittal linked to ACE design verification/rejection letters | High | Weak to Moderate | Contractor weak; Contractor weak | Medium | Medium; Medium | Resubmit consultant package if not approved
Geotechnical tests / soil recommendation | BD-CW-SAMCO-ACE-LET-STR-036 | 37 | 21-Dec-2025 | Variation Request | Request for VI - CPTu and DCPT Works | BD-ACEPM-SAMCO-LET-013 | 14 | 05-Oct-2025 | BD-ACEPM-SAMCO-LET-013 - Soil replacement recommendation | Same geotechnical instruction thread | Medium | Moderate | Moderate if scope changes | Low to Medium | Medium | Issue VI/valuation for extra tests if instructed
IFC drawings / design review | BD-CW-SAMCO-ACE-LET-STR-019 | 20 | 26-Oct-2025 | Design Request | Request for Complete Set of IFC Drawings | BD-ACEPM-SAMCO-LET-020 | 21 | 08-Dec-2025 | BD-ACEPM-SAMCO-LET-020 - Design review | Same design information thread | Medium | Moderate to Strong | Contractor weak | High | High | Confirm complete IFC issue dates and design change impact
Insurance | BD-CW-SAMCO-ACE-LET-STR-021 | 22 | 29-Oct-2025 | Insurance Undertaking | Contractor Commitment to Maintain Required Insurance | BD-ACEPM-SAMCO-LET-007 | 8 | 22-Sep-2025 | BD-ACEPM-SAMCO-LET-007 - Insurance policy | Response/undertaking after ACE insurance rejection | High |  | Contractor weak | Low | Medium | Close insurance compliance evidence
IPC / payment | BD-CW-SAMCO-ACE-LET-STR-046 | 47 | 24-Jan-2026 | Payment Submission | Submission of Interim Payment Certificate No. 3 | BD-ACEPM-SAMCO-LET-027; BD-ACEPM-SAMCO-LET-031 | 28; 32 | 15-Feb-2026; 19-Apr-2026 | BD-ACEPM-SAMCO-LET-027 - Required breakdown delay ¦ BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | IPC submission linked to payment/breakdown correspondence | Medium |  | Contractor weak; Contractor weak | Low | Low; Low | Track certification and payment date
IPC / payment / breakdown | BD-CW-SAMCO-ACE-LET-STR-028 | 29 | 06-Dec-2025 | Payment Submission | Submission of Interim Payment Certificate No. 1 | BD-ACEPM-SAMCO-LET-027; BD-ACEPM-SAMCO-LET-031 | 28; 32 | 15-Feb-2026; 19-Apr-2026 | BD-ACEPM-SAMCO-LET-027 - Required breakdown delay ¦ BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | IPC submission later affected by breakdown/payment correspondence | Medium |  | Contractor weak; Contractor weak | Low | Low; Low | Track certification, breakdown and payment dates
IPC / payment recommendation | BD-CW-SAMCO-ACE-LET-STR-038 | 39 | 21-Jan-2026 | Payment Recommendation / Attachment | ACEPM Recommendation of Monthly Interim Payment No. 2 | BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | Related IPC/payment thread; document is ACEPM/Roya attachment | Medium |  | Contractor weak | Low | Low | Treat as payment support, not SAMCO cover letter
IPC payment | BD-CW-SAMCO-ACE-LET-STR-056 | 57 | 25-Feb-2026 | Payment Submission | Submission of Interim Payment Certificate No. 4 | BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | Same IPC payment thread | Medium |  | Contractor weak | Low | Low | Track IPC 4 certification/payment
IPC payment | BD-CW-SAMCO-ACE-LET-STR-059 | 60 | 25-Mar-2026 | Payment Submission | Submission of Interim Payment Certificate No. 5 | BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | Same IPC payment thread | Medium |  | Contractor weak | Low | Low | Track IPC 5 due date/payment
IPC payment delay | BD-CW-SAMCO-ACE-LET-STR-054 | 55 | 24-Feb-2026 | Payment Delay Notice | IPC Payment Status | BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | Directly answered by ACE payment clarification | High | Moderate | Contractor weak | Medium | Low | Reconcile due dates, thresholds and delay interest
IPC payment delay | BD-CW-SAMCO-ACE-LET-STR-055 | 56 | 24-Feb-2026 | Payment Record | Actual Receipt Date of Cheque - IPC 1 | BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | Same IPC payment thread | High | Moderate | Contractor weak | Low | Low | Use actual cheque receipt date in payment analysis
IPC payment delay | BD-CW-SAMCO-ACE-LET-STR-068 | 69 | 16-Apr-2026 | Payment Delay Notice | Follow-up on Settlement of IPCs | BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | Directly answered by ACE payment clarification | High | Moderate to Strong | Contractor weak | Medium | Low | Reconcile IPC chronology and payment entitlement
MEP coordination / first fix | BD-CW-SAMCO-ACE-LET-STR-016 | 17 | 07-Oct-2025 | Contract Position / Reservation | Clarification Regarding Coordination Responsibilities | BD-ACEPM-SAMCO-LET-017; BD-ACEPM-SAMCO-LET-025 | 18; 26 | 26-Nov-2025; 27-Jan-2026 | BD-ACEPM-SAMCO-LET-017 - VI-0003 rejection ¦ BD-ACEPM-SAMCO-LET-025 - MEP first fix variation | Same MEP responsibility dispute thread | Medium | Moderate | Employer strong; Employer strong | High | High; High | Resolve scope by instruction/variation and MEP package
MEP first fix | BD-CW-SAMCO-ACE-LET-STR-049 | 50 | 29-Jan-2026 | Response / Conditional Acceptance | Response to LET-025 First Fix MEP Works | BD-ACEPM-SAMCO-LET-025; BD-ACEPM-SAMCO-LET-026 | 26; 27 | 27-Jan-2026; 02-Feb-2026 | BD-ACEPM-SAMCO-LET-025 - MEP first fix variation ¦ BD-ACEPM-SAMCO-LET-026 - Response to LET-025 | Direct response to ACE first-fix interpretation/clarification | High | Moderate | Employer strong; Moderate if procedure followed | High | High; High | Issue/price VO and monitor execution
MEP package / first fix | BD-CW-SAMCO-ACE-LET-STR-032 | 33 | 11-Dec-2025 | Design Request | Request for Complete Package for Coordination - TRA-007 | BD-ACEPM-SAMCO-LET-025; BD-ACEPM-SAMCO-LET-026 | 26; 27 | 27-Jan-2026; 02-Feb-2026 | BD-ACEPM-SAMCO-LET-025 - MEP first fix variation ¦ BD-ACEPM-SAMCO-LET-026 - Response to LET-025 | Same MEP first-fix coordination thread | Medium | Moderate | Employer strong; Moderate if procedure followed | Medium to High | High; High | Issue complete MEP basement/foundation package
MOM additions / commercial terms | BD-CW-SAMCO-ACE-LET-STR-047 | 48 | 24-Jan-2026 | MOM Correction / Commercial Record | Additions to MOM - Coordination Meeting 19-Jan-2026 | BD-ACEPM-SAMCO-LET-024; BD-ACEPM-SAMCO-LET-031 | 25; 32 | 22-Jan-2026; 19-Apr-2026 | BD-ACEPM-SAMCO-LET-024 - Adopted design criteria ¦ BD-ACEPM-SAMCO-LET-031 - IPC settlement follow-up | Links to design criteria and payment/security discussions | Medium | Moderate | Contractor weak; Contractor weak | Low to Medium | Medium; Low | Update MOM and commercial record
Outstanding deliverables / tower cranes | BD-CW-SAMCO-ACE-LET-STR-003 | 4 | 30-Jun-2025 | Response / Reservation | RE: Outstanding Deliverables - Urgent Response Required | BD-ACEPM-SAMCO-LET-001; BD-ACEPM-SAMCO-LET-002 | 2; 3 | 24-Jun-2025; 25-Jun-2025 | BD-ACEPM-SAMCO-LET-001 - Outstanding Deliverables ¦ BD-ACEPM-SAMCO-LET-002 - Tower Crane No. 1 delay | Direct response to ACE notices | High | Moderate | Contractor weak; Contractor weak | High | High; High | Close remaining deliverables and confirm baseline dependency
Periodic reports / programme | BD-CW-SAMCO-ACE-LET-STR-033 | 34 | 15-Dec-2025 | Response / Reporting Position | Response to LET-021 Periodic Reports | BD-ACEPM-SAMCO-LET-021 | 22 | 10-Dec-2025 | BD-ACEPM-SAMCO-LET-021 - Periodic reports delay | Direct response to ACE reporting notice | High | Weak to Moderate | Contractor weak | Medium | Medium | Agree baseline/reporting basis
Pipe breakage / leakage impact | BD-CW-SAMCO-ACE-LET-STR-014 | 15 | 05-Oct-2025 | Notice / Reservation | Implications of Water Pipe Break | BD-ACEPM-SAMCO-LET-011; BD-ACEPM-SAMCO-LET-023 | 12; 24 | 04-Oct-2025; 11-Jan-2026 | BD-ACEPM-SAMCO-LET-011 - Pipe breakage/excavation ¦ BD-ACEPM-SAMCO-LET-023 - Water pipeline leakage | Same leakage/impact thread | Medium | Moderate to Strong | Contractor weak; Contractor weak | High | Low/Medium; Low | Separate incident impact from later closed leakage position
Pipe breakage / tank excavation | BD-CW-SAMCO-ACE-LET-STR-012 | 13 | 30-Sep-2025 | Meeting Follow-up | Meeting Minutes and Follow-up on Discussed Points | BD-ACEPM-SAMCO-LET-011 | 12 | 04-Oct-2025 | BD-ACEPM-SAMCO-LET-011 - Pipe breakage/excavation | Same incident thread | Medium | Moderate | Contractor weak | High | Low/Medium | Confirm repair status and restart logic
Pipe breakage / tank excavation | BD-CW-SAMCO-ACE-LET-STR-013 | 14 | 30-Sep-2025 | Notice of Suspension | Pipe Breakage and Suspension of Excavation Works | BD-ACEPM-SAMCO-LET-011 | 12 | 04-Oct-2025 | BD-ACEPM-SAMCO-LET-011 - Pipe breakage/excavation | Directly addressed by ACE response | High | Moderate | Contractor weak | High | Low/Medium | Record repair completion and affected period
Project status / design / steel | BD-CW-SAMCO-ACE-LET-STR-052 | 53 | 16-Feb-2026 | Status Update / Reservation | Project Status Update - Buildings B1 to B17 | BD-ACEPM-SAMCO-LET-022; BD-ACEPM-SAMCO-LET-024; BD-ACEPM-SAMCO-LET-028; BD-ACEPM-SAMCO-LET-029 | 23; 25; 29; 30 | 28-Dec-2025; 22-Jan-2026; 16-Feb-2026; 24-Feb-2026 | BD-ACEPM-SAMCO-LET-022 - Design review ¦ BD-ACEPM-SAMCO-LET-024 - Adopted design criteria ¦ BD-ACEPM-SAMCO-LET-028 - Steel supply status ¦ BD-ACEPM-SAMCO-LET-029 - Project status update | Status update linked to multiple ACE positions | Medium | Moderate | Weak/uncertain; Contractor weak; Weak to moderate; Contractor weak | High | High; Medium; High; Low | Separate routine status from claim notices
Project status updates | BD-CW-SAMCO-ACE-LET-STR-020 | 21 | 27-Oct-2025 | Status Update / Reservation | Project Status Update - Buildings B1 to B17 | BD-ACEPM-SAMCO-LET-029 | 30 | 24-Feb-2026 | BD-ACEPM-SAMCO-LET-029 - Project status update | ACE later rejects status letters as contractual basis | Medium | Moderate | Contractor weak | Medium to High | Low | Use reports/MOMs for routine status and notices for claims
Project status updates | BD-CW-SAMCO-ACE-LET-STR-022 | 23 | 23-Nov-2025 | Status Update / Reservation | Project Status Update - Buildings B1 to B17 | BD-ACEPM-SAMCO-LET-029 | 30 | 24-Feb-2026 | BD-ACEPM-SAMCO-LET-029 - Project status update | ACE later rejects status letters as contractual basis | Medium | Moderate | Contractor weak | Medium to High | Low | Move progress content into formal reports
Project status updates | BD-CW-SAMCO-ACE-LET-STR-037 | 38 | 24-Dec-2025 | Status Update / Request | Project Status Update - Buildings B1 to B17 | BD-ACEPM-SAMCO-LET-029 | 30 | 24-Feb-2026 | BD-ACEPM-SAMCO-LET-029 - Project status update | ACE later rejects status letters as contractual basis | Medium | Moderate | Contractor weak | Medium to High | Low | Shift progress updates into approved reports
Ramp / access route | BD-CW-SAMCO-ACE-LET-STR-008 | 9 | 24-Sep-2025 | Claim Notice / Reservation | Response Regarding Site Ramp Modification Works | BD-ACEPM-SAMCO-LET-008 | 9 | 28-Sep-2025 | BD-ACEPM-SAMCO-LET-008 - Site ramp works | Directly related to ACE claim rejection | High | Moderate | Contractor weak | Medium | Medium | Determine whether access work is contractor obligation or variation
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-010 | 11 | 25-Sep-2025 | Procurement Request | Supply of reinforcement steel for the project | BD-ACEPM-SAMCO-LET-016 | 17 | 20-Oct-2025 | BD-ACEPM-SAMCO-LET-016 - Reinforcement steel quantity | Same steel requisition thread | Medium | Moderate | Moderate if owner delay proven | Medium | Medium | Confirm owner supply priority and delivery
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-011 | 12 | 29-Sep-2025 | Procurement Revision / Coordination | Request to Reduce First Reinforcement Steel Delivery | BD-ACEPM-SAMCO-LET-016 | 17 | 20-Oct-2025 | BD-ACEPM-SAMCO-LET-016 - Reinforcement steel quantity | Directly addressed by ACE response | High | Moderate | Moderate if owner delay proven | Medium | Medium | Align revised first delivery quantity
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-025 | 26 | 26-Nov-2025 | Procurement Request | Supply of Reinforcement Steel - Second Delivery | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Same steel delay thread | Medium | Moderate | Weak to moderate | Medium | High | Track order 2 delivery dates and mitigation
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-042 | 43 | 06-Jan-2026 | Procurement Request | Supply of Reinforcement Steel - Third Delivery | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Same steel delay/supply thread | Medium | Moderate | Weak to moderate | Medium | High | Track third order delivery
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-044 | 45 | 15-Jan-2026 | Procurement Delay Notice | Delay in Supplying Reinforcement Steel | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Directly related to ACE steel rebuttal | High | Moderate to Strong | Weak to moderate | High | High | Measure supply delay, mitigation and schedule impact
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-048 | 49 | 26-Jan-2026 | Procurement Delay Notice | Follow-up on Delay of Reinforcement Steel Delivery | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Directly related to ACE steel rebuttal | High | Moderate to Strong | Weak to moderate | High | High | Assess near-suspension and EOT notice compliance
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-051 | 52 | 07-Feb-2026 | Procurement Delay / EOT Notice | Reinforcement Steel Supply Status and EOT Entitlement | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Directly related to ACE steel rebuttal | High | Moderate to Strong | Weak to moderate | High | High | Track SAMCO-supplied 300 tons and EOT basis
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-053 | 54 | 24-Feb-2026 | Procurement Delay / Commercial Claim Reservation | Reinforcement Steel Order No. 2 Delay | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Directly related to ACE steel rebuttal | High | Strong | Weak to moderate | High | High | Approve revised distribution and certify mitigation steel
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-062 | 63 | 31-Mar-2026 | Procurement Delay Notice | Follow-up on Reinforcement Steel Delivery | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Same steel delay thread after ACE rebuttal | High | Strong | Weak to moderate | High | High | Update cumulative delay and mitigation record
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-069 | 70 | 19-Apr-2026 | Procurement Delay / Cumulative Impact Notice | Follow-up on Reinforcement Steel Supply and Cumulative Project Impact | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Same cumulative steel delay thread | High | Strong | Weak to moderate | High | High | Assess cumulative EOT/cost and owner supply record
Reinforcement steel supply / guarantee cheque | BD-CW-SAMCO-ACE-LET-STR-045 | 46 | 22-Jan-2026 | Commercial Submission | Guarantee Cheque for Reinforcement Steel | BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | BD-ACEPM-SAMCO-LET-028 - Steel supply status | Same steel supply arrangement thread | Medium |  | Weak to moderate | Low | High | Confirm cheque acceptance and release steel
RFI delay claim | BD-CW-SAMCO-ACE-LET-STR-064 | 65 | 02-Apr-2026 | Notice of Claim | Delay in Technical Clarifications |  |  |  |  | No direct ACE response in table | Low | Strong |  | High |  | Link to RFI response log when available
Site obstacles / water leakage | BD-CW-SAMCO-ACE-LET-STR-005 | 6 | 10-Sep-2025 | Notice of Delay / Site Obstacle | RE: Documentation of Site Obstacles Affecting Project Progress | BD-ACEPM-SAMCO-LET-005 | 6 | 17-Sep-2025 | BD-ACEPM-SAMCO-LET-005 - Site obstacles B1-B4 | Directly referenced by ACE response | High | Moderate | Contractor weak | High | Low | Substantiate any EOT with programme and records
Site obstacles / water leakage | BD-CW-SAMCO-ACE-LET-STR-007 | 8 | 24-Sep-2025 | Response / Reservation | RE: Response to Letter No. BD-ACEPM-SAMCO-LET-005 | BD-ACEPM-SAMCO-LET-005 | 6 | 17-Sep-2025 | BD-ACEPM-SAMCO-LET-005 - Site obstacles B1-B4 | Follow-up response on same issue | High | Moderate | Contractor weak | Medium | Low | Maintain claim records and approval history
Soil replacement delay | BD-CW-SAMCO-ACE-LET-STR-018 | 19 | 13-Oct-2025 | Response / Delay Mitigation | Response Regarding Delay of Works at Site | BD-ACEPM-SAMCO-LET-014; BD-ACEPM-SAMCO-LET-015 | 15; 16 | 12-Oct-2025; 15-Oct-2025 | BD-ACEPM-SAMCO-LET-014 - Soil replacement B1/B2 ¦ BD-ACEPM-SAMCO-LET-015 - Delay of works at site | Direct response to ACE delay letters | High | Moderate | Employer strong; Contractor weak | High | High; High | Clarify instruction to proceed pending tests and ramp status
Survey / batching plant / Zone 2 | BD-CW-SAMCO-ACE-LET-STR-004 | 5 | 28-Aug-2025 | Notice / Site Condition | RE: Site Survey Findings and Allocation of Concrete Batching Plant | BD-ACEPM-SAMCO-LET-003 | 4 | 31-Aug-2025 | BD-ACEPM-SAMCO-LET-003 - Survey and batching plant | Directly related by subject and ACE response | High | Moderate | Moderate if owner-caused | High | Medium | Close survey, batching plant and handover decisions
Technical responses / coordinated drawings | BD-CW-SAMCO-ACE-LET-STR-057 | 58 | 11-Mar-2026 | Delay Notice / Design Information | Delayed Technical Responses and Outstanding Coordinated Drawings |  |  |  |  | No direct ACE response in table | Low | Strong |  | High |  | Prepare separate claim chronology for RFIs
Utility protection variation | BD-CW-SAMCO-ACE-LET-STR-017 | 18 | 09-Oct-2025 | Variation Response / Rejection | Response to VI ROYA-BIG-2025-VI-001 |  |  |  |  | No direct ACE response in table | Low | Strong |  | High |  | Link to separate VI file if available
Variation procedure / IFC package | BD-CW-SAMCO-ACE-LET-STR-015 | 16 | 06-Oct-2025 | Document Request | Reminder to Submit Final Package and Signed Hard Copies | BD-ACEPM-SAMCO-LET-012 | 13 | 05-Oct-2025 | BD-ACEPM-SAMCO-LET-012 - Variation procedure | Response to ACE variation procedure notice | High | Moderate | Depends on compliance | Medium | Low | Issue complete IFC package or preserve notice rights
VI-0003 / flanges / MEP | BD-CW-SAMCO-ACE-LET-STR-035 | 36 | 18-Dec-2025 | Variation Rejection / Contract Position | Response to LET-019 and VI-0003 | BD-ACEPM-SAMCO-LET-019; BD-ACEPM-SAMCO-LET-025 | 20; 26 | 04-Dec-2025; 27-Jan-2026 | BD-ACEPM-SAMCO-LET-019 - GWT flanges ¦ BD-ACEPM-SAMCO-LET-025 - MEP first fix variation | Direct response to ACE flanges rebuttal | High | Moderate | Employer strong; Employer strong | High | High; High | Resolve flanges scope and formal variation position
VI-0003 / MEP works | BD-CW-SAMCO-ACE-LET-STR-024 | 25 | 24-Nov-2025 | Variation Rejection | Response to VI BD-ACEPM-SAMCO-VI-0003 | BD-ACEPM-SAMCO-LET-017 | 18 | 26-Nov-2025 | BD-ACEPM-SAMCO-LET-017 - VI-0003 rejection | Directly referenced by ACE enforcement letter | High | Moderate | Employer strong | High | High | Resolve disputed scope and proceed under formal instruction
VI-0003 / MEP works / flanges | BD-CW-SAMCO-ACE-LET-STR-027 | 28 | 30-Nov-2025 | Formal Rejection / Reservation | Formal Rejection of Assigning MEP Works | BD-ACEPM-SAMCO-LET-017; BD-ACEPM-SAMCO-LET-019; BD-ACEPM-SAMCO-LET-025 | 18; 20; 26 | 26-Nov-2025; 04-Dec-2025; 27-Jan-2026 | BD-ACEPM-SAMCO-LET-017 - VI-0003 rejection ¦ BD-ACEPM-SAMCO-LET-019 - GWT flanges ¦ BD-ACEPM-SAMCO-LET-025 - MEP first fix variation | Directly related to ACE rebuttals and interpretation letters | High | Moderate | Employer strong; Employer strong; Employer strong | High | High; High; High | Settle MEP/flange scope and valuation route
Water pipeline leakage | BD-CW-SAMCO-ACE-LET-STR-039 | 40 | 04-Jan-2026 | Notice / Site Incident | Water Pipeline Leakage and Its Impact on Project Works | BD-ACEPM-SAMCO-LET-023 | 24 | 11-Jan-2026 | BD-ACEPM-SAMCO-LET-023 - Water pipeline leakage | Directly answered by ACE closure letter | High | Moderate | Contractor weak | Medium | Low | Confirm no residual impact or document rework separately
Waterproofing materials | BD-CW-SAMCO-ACE-LET-STR-023 | 24 | 23-Nov-2025 | Technical Query | Related to Waterproofing Works |  |  |  |  | No direct ACE response in table | Low | Moderate |  | Medium |  | Request/locate waterproofing clarification response
Weather | BD-CW-SAMCO-ACE-LET-STR-058 | 59 | 14-Mar-2026 | Weather Notice | Work Suspension Due to Severe Weather |  |  |  |  | No direct ACE response in table | Low | Weak |  | Low |  | Keep weather log only
Weather | BD-CW-SAMCO-ACE-LET-STR-060 | 61 | 25-Mar-2026 | Weather Notice | Work Interruption Due to Adverse Weather |  |  |  |  | No direct ACE response in table | Low | Weak to Moderate |  | Medium |  | Keep weather log only
Weather | BD-CW-SAMCO-ACE-LET-STR-061 | 62 | 29-Mar-2026 | Weather Notice | Work Interruption Due to Adverse Weather |  |  |  |  | No direct ACE response in table | Low | Weak to Moderate |  | Medium |  | Keep weather log only
Weather | BD-CW-SAMCO-ACE-LET-STR-065 | 66 | 02-Apr-2026 | Weather Notice | Work Interruption Due to Adverse Weather |  |  |  |  | No direct ACE response in table | Low | Weak to Moderate |  | Medium |  | Keep weather log only
Weather / insulation | BD-CW-SAMCO-ACE-LET-STR-031 | 32 | 11-Dec-2025 | Weather Notice | Postponement of Insulation Works Due to Weather |  |  |  |  | No direct ACE response in table | Low | Weak |  | Low |  | Keep weather record only
Weather / tower cranes | BD-CW-SAMCO-ACE-LET-STR-043 | 44 | 12-Jan-2026 | Weather Notice | Suspension of Tower Crane Operations |  |  |  |  | No direct ACE response in table | Low | Weak |  | Low |  | Keep weather/crane log only
Site progress / steel supply / RFI 17 / B1-B4 structural package | BD-CW-SAMCO-ACE-LET-STR-071 | 72 | 27-Apr-2026 | Early Warning / Notice under Sub-Clause 20.1 | Early Warning & Notification of Fact – Site Progress and Constraints for Buildings B1-B4 | BD-ACEPM-SAMCO-LET-033 | 33 | 05-May-2026 | Re: Early Warning & Notification of Fact (pursuant to Sub-Clause 20.1) – Site Progress and Constraints for Buildings B1-B4 | ACE response rejects the notice on procedural grounds and requires a compliant claim | High | Strong | ACE strong procedurally / Contractor weak on compliance | High | Medium | Convert the notice into a formal Sub-Clause 20.1 claim with supporting delay/cost evidence and response to the RFI/design discrepancy issue
Payments / IPCs / breakdown | BD-CW-SAMCO-ACE-LET-STR-070 | 71 | 25-Apr-2026 | Payment Submission | Submission of Interim Payment Certificate No. 6 |  |  |  |  | Same IPC / payment thread; no direct ACE response in current source table | Medium |  |  | Low |  | Review, certify, and pay IPC 6 within the contractual period
MEP / first fix / flanges / VI-0003 | BD-CW-SAMCO-ACE-LET-STR-072 | 73 | 27-Apr-2026 | Submission / Meeting Minutes | Submission of Minutes of Meetings - MEP Works (First Fix). |  |  |  |  | Same MEP first-fix coordination thread; no direct ACE response identified in the current source table | Medium | Moderate to Strong |  | High |  | Formalize first-fix responsibilities and close outstanding design conflicts
Waterproofing materials | BD-CW-SAMCO-ACE-LET-STR-073 | 74 | 28-Apr-2026 | Clarification / Technical Notice | Scope Clarification - Internal Tank Waterproofing. |  |  |  |  | No direct ACE response in current source table | Low | Moderate |  | Medium |  | Locate Engineer decision on internal waterproofing system and execution route
Contractual submissions / reports | BD-CW-SAMCO-ACE-LET-STR-074 | 75 | 29-Apr-2026 | Response / Reporting Compliance | Re: Non-Compliance with Submission of Weekly Progress Reports. | BD-ACEPM-SAMCO-LET-032 |  |  |  | Direct response to ACE weekly reporting notice; ACE source letter is not available in the current workbook | High | Weak to Moderate |  | Medium |  | Submit the overdue weekly reports and close the reporting-compliance issue formally
Payments / IPCs / breakdown | BD-CW-SAMCO-ACE-LET-STR-075 | 76 | 30-Apr-2026 | Commercial Response / Reservation | Re: BD-ACEPM-SAMCO-LET-031 | BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | IPC settlement follow-up | Direct response to ACE IPC clarification / threshold letter | High | Moderate | Contractor weak | Medium | Low | Reconcile IPC thresholds, due dates, and the constraint-driven reduction in certified values
Site progress / steel supply / RFI 17 / structural package discrepancy | BD-CW-SAMCO-ACE-LET-STR-076 | 77 | 09-May-2026 | Notice of Claim / Design Discrepancy | Notice of Claim - Impact of Revised Structural Drawings on Project Progress [Sub-Clause 1.9 / 8.4 / 20.1] |  |  |  |  | Follow-on design package claim within the same structural discrepancy thread; no direct ACE reply in the current source table | Medium | Strong |  | High |  | Convert the design discrepancy chronology into a full cause-effect claim with hold period evidence
Retaining wall backfilling variation | BD-CW-SAMCO-ACE-LET-STR-077 | 78 | 11-May-2026 | Variation Notice / Reservation of Rights | Notice of Variation and Reservation of Rights - Backfilling Works Behind Retaining Wall. |  |  |  |  | No direct ACE response in current source table | Low | Strong |  | High |  | Issue VO, measure the work, and assess the critical-path impact of delayed instruction
MEP / first fix / flanges / VI-0003 | BD-CW-SAMCO-ACE-LET-STR-078 | 79 | 11-May-2026 | Meeting Minutes Submission | Submission of MOM - Site Meeting for Mechanical Works (First Fix) Held on Wednesday 06/05/2026. |  |  |  |  | Same MEP first-fix coordination thread; no direct ACE response identified in the current source table | Medium | Moderate |  | Medium |  | Track closure of MEP first-fix action items and preserve interface records
Reinforcement steel supply | BD-CW-SAMCO-ACE-LET-STR-079 | 80 | 24-May-2026 | Procurement Delay / EOT Response | Reply to Notification of Reinforcement Steel Supply Status and Entitlement to Time Extensions | BD-ACEPM-SAMCO-LET-035 | 35 | 11-May-2026 | Re: Notification of Reinforcement Steel Supply Status and Entitlement to Time Extensions | Direct response to ACE steel supply / time-extension position | High | Strong |  | High |  | Reconcile delivery dates, pending quantities, and the updated time-impact narrative
Site progress / steel supply / RFI 17 / structural package discrepancy | BD-CW-SAMCO-ACE-LET-STR-080 | 81 | 24-May-2026 | Delay Notice Response / Reservation | Response to Notice - Alleged Failure to Achieve Section (1) Milestone | BD-ACEPM-SAMCO-LET-036 | 36 | 11-May-2026 | Failure to Achieve Section (1) Milestone within the Contractual Due Date | Direct response to ACE milestone-failure notice | High | Strong |  | High |  | Tie the milestone miss to explicit steel, IFC, and RFI cause-effect records and submit the revised plan
Payments / IPCs / breakdown | BD-CW-SAMCO-ACE-LET-STR-081 | 82 | 24-May-2026 | Payment Submission | Submission of Interim Payment Certificate No. 7 |  |  |  |  | Same IPC / payment thread; no direct ACE response in current source table | Medium |  |  | Low |  | Review, certify, and pay IPC 7 within the contractual period
Waterproofing materials | BD-CW-SAMCO-ACE-LET-STR-082 | 83 | 25-May-2026 | Clarification / Claim Notice | Clarification on Internal Waterproofing System, Execution Sequence and Performance Warranty - Water Tank. |  |  |  |  | No direct ACE response in current source table; this is a follow-on clarification / claim notice to STR-073 and the tank RFI | Medium | Moderate to Strong |  | High |  | Resolve the waterproofing system decision and preserve the sequence / warranty claim record

## ACE to SAMCO Links
ACE Ref No | ACE Sheet Row | ACE Date | ACE Type | ACE Subject | Related SAMCO Ref No(s) | SAMCO Sheet Row(s) | SAMCO Subject(s) | Thread(s) | ACE Delay Risk | ACE EOT Potential | ACE Claim Strength | ACE Required Actions
BD-ACEPM-SAMCO-LET-001 | 2 | 24-Jun-2025 | Notice | Outstanding Deliverables | BD-CW-SAMCO-ACE-LET-STR-003 | 4 | BD-CW-SAMCO-ACE-LET-STR-003 - RE: Outstanding Deliverables - Urgent Response Required | Outstanding deliverables / tower cranes | High | Low | Contractor weak | Submit all overdue items
BD-ACEPM-SAMCO-LET-002 | 3 | 25-Jun-2025 | Delay notice | Tower Crane No. 1 delay | BD-CW-SAMCO-ACE-LET-STR-003 | 4 | BD-CW-SAMCO-ACE-LET-STR-003 - RE: Outstanding Deliverables - Urgent Response Required | Outstanding deliverables / tower cranes | High | Low | Contractor weak | Install TC1 immediately
BD-ACEPM-SAMCO-LET-003 | 4 | 31-Aug-2025 | Clarification | Survey and batching plant | BD-CW-SAMCO-ACE-LET-STR-004 | 5 | BD-CW-SAMCO-ACE-LET-STR-004 - RE: Site Survey Findings and Allocation of Concrete Batching Plant | Survey / batching plant / Zone 2 | Medium | Conditional | Moderate if owner-caused | Close reviews and approvals
BD-ACEPM-SAMCO-LET-004 | 5 | 17-Sep-2025 | Submission notice | Required contractual submissions | BD-CW-SAMCO-ACE-LET-STR-006 | 7 | BD-CW-SAMCO-ACE-LET-STR-006 - RE: Response to Letter No. BD-ACEPM-SAMCO-LET-004 | Contractual submissions | High | Low | Contractor weak | Submit full package
BD-ACEPM-SAMCO-LET-005 | 6 | 17-Sep-2025 | Response | Site obstacles B1-B4 | BD-CW-SAMCO-ACE-LET-STR-005; BD-CW-SAMCO-ACE-LET-STR-007 | 6; 8 | BD-CW-SAMCO-ACE-LET-STR-005 - RE: Documentation of Site Obstacles Affecting Project Progress ¦ BD-CW-SAMCO-ACE-LET-STR-007 - RE: Response to Letter No. BD-ACEPM-SAMCO-LET-005 | Site obstacles / water leakage | Low | Low | Contractor weak | Submit compliant claim if any
BD-ACEPM-SAMCO-LET-006 | 7 | 22-Sep-2025 | Reminder | Design verification | BD-CW-SAMCO-ACE-LET-STR-009 | 10 | BD-CW-SAMCO-ACE-LET-STR-009 - Submission of Consultant CV and Approval Certificate | Design verification consultant | Medium | Low | Contractor weak | Submit prequalification/report
BD-ACEPM-SAMCO-LET-007 | 8 | 22-Sep-2025 | Rejection | Insurance policy | BD-CW-SAMCO-ACE-LET-STR-021 | 22 | BD-CW-SAMCO-ACE-LET-STR-021 - Contractor Commitment to Maintain Required Insurance | Insurance | Medium | Low | Contractor weak | Resubmit complete policies
BD-ACEPM-SAMCO-LET-008 | 9 | 28-Sep-2025 | Claim rejection | Site ramp works | BD-CW-SAMCO-ACE-LET-STR-008 | 9 | BD-CW-SAMCO-ACE-LET-STR-008 - Response Regarding Site Ramp Modification Works | Ramp / access route | Medium |  | Contractor weak | Maintain ramp and proceed
BD-ACEPM-SAMCO-LET-009 | 10 | 28-Sep-2025 | Access clarification | Borehole locations |  |  |  |  | Low | Conditional | Moderate if owner blocks access | Formalize approvals
BD-ACEPM-SAMCO-LET-010 | 11 | 02-Oct-2025 | Submittal rejection | Consultant CV/design review | BD-CW-SAMCO-ACE-LET-STR-009 | 10 | BD-CW-SAMCO-ACE-LET-STR-009 - Submission of Consultant CV and Approval Certificate | Design verification consultant | Medium | Low | Contractor weak | Resubmit consultant package
BD-ACEPM-SAMCO-LET-011 | 12 | 04-Oct-2025 | Response/instruction | Pipe breakage/excavation | BD-CW-SAMCO-ACE-LET-STR-012; BD-CW-SAMCO-ACE-LET-STR-013; BD-CW-SAMCO-ACE-LET-STR-014 | 13; 14; 15 | BD-CW-SAMCO-ACE-LET-STR-012 - Meeting Minutes and Follow-up on Discussed Points ¦ BD-CW-SAMCO-ACE-LET-STR-013 - Pipe Breakage and Suspension of Excavation Works ¦ BD-CW-SAMCO-ACE-LET-STR-014 - Implications of Water Pipe Break | Pipe breakage / leakage impact; Pipe breakage / tank excavation | Low/Medium | Low | Contractor weak | Execute rectification
BD-ACEPM-SAMCO-LET-012 | 13 | 05-Oct-2025 | Procedure notice | Variation procedure | BD-CW-SAMCO-ACE-LET-STR-015 | 16 | BD-CW-SAMCO-ACE-LET-STR-015 - Reminder to Submit Final Package and Signed Hard Copies | Variation procedure / IFC package | Low | Conditional | Depends on compliance | Follow 13.3 notice process
BD-ACEPM-SAMCO-LET-013 | 14 | 05-Oct-2025 | Technical instruction | Soil replacement recommendation | BD-CW-SAMCO-ACE-LET-STR-036 | 37 | BD-CW-SAMCO-ACE-LET-STR-036 - Request for VI - CPTu and DCPT Works | Geotechnical tests / soil recommendation | Medium | Conditional | Moderate if scope changes | Implement comments
BD-ACEPM-SAMCO-LET-014 | 15 | 12-Oct-2025 | Delay notice | Soil replacement B1/B2 | BD-CW-SAMCO-ACE-LET-STR-018 | 19 | BD-CW-SAMCO-ACE-LET-STR-018 - Response Regarding Delay of Works at Site | Soil replacement delay | High | Low | Employer strong | Mobilize and test
BD-ACEPM-SAMCO-LET-015 | 16 | 15-Oct-2025 | Response | Delay of works at site | BD-CW-SAMCO-ACE-LET-STR-018 | 19 | BD-CW-SAMCO-ACE-LET-STR-018 - Response Regarding Delay of Works at Site | Soil replacement delay | High | Low | Contractor weak | Proceed and maintain access
BD-ACEPM-SAMCO-LET-016 | 17 | 20-Oct-2025 | Coordination response | Reinforcement steel quantity | BD-CW-SAMCO-ACE-LET-STR-010; BD-CW-SAMCO-ACE-LET-STR-011 | 11; 12 | BD-CW-SAMCO-ACE-LET-STR-010 - Supply of reinforcement steel for the project ¦ BD-CW-SAMCO-ACE-LET-STR-011 - Request to Reduce First Reinforcement Steel Delivery | Reinforcement steel supply | Medium | Conditional | Moderate if owner delay proven | Confirm quantities/delivery
BD-ACEPM-SAMCO-LET-017 | 18 | 26-Nov-2025 | Variation enforcement | VI-0003 rejection | BD-CW-SAMCO-ACE-LET-STR-016; BD-CW-SAMCO-ACE-LET-STR-024; BD-CW-SAMCO-ACE-LET-STR-027 | 17; 25; 28 | BD-CW-SAMCO-ACE-LET-STR-016 - Clarification Regarding Coordination Responsibilities ¦ BD-CW-SAMCO-ACE-LET-STR-024 - Response to VI BD-ACEPM-SAMCO-VI-0003 ¦ BD-CW-SAMCO-ACE-LET-STR-027 - Formal Rejection of Assigning MEP Works | MEP coordination / first fix; VI-0003 / MEP works; VI-0003 / MEP works / flanges | High | Low | Employer strong | Execute VI; submit proposal
BD-ACEPM-SAMCO-LET-018 | 19 | 03-Dec-2025 | Non-compliance notice | Programme delay |  |  |  |  | High | Low | Contractor weak | Resubmit program
BD-ACEPM-SAMCO-LET-019 | 20 | 04-Dec-2025 | Variation rebuttal | GWT flanges | BD-CW-SAMCO-ACE-LET-STR-027; BD-CW-SAMCO-ACE-LET-STR-035 | 28; 36 | BD-CW-SAMCO-ACE-LET-STR-027 - Formal Rejection of Assigning MEP Works ¦ BD-CW-SAMCO-ACE-LET-STR-035 - Response to LET-019 and VI-0003 | VI-0003 / flanges / MEP; VI-0003 / MEP works / flanges | High | Low | Employer strong | Execute works
BD-ACEPM-SAMCO-LET-020 | 21 | 08-Dec-2025 | Delay notice | Design review | BD-CW-SAMCO-ACE-LET-STR-019; BD-CW-SAMCO-ACE-LET-STR-026; BD-CW-SAMCO-ACE-LET-STR-029; BD-CW-SAMCO-ACE-LET-STR-030 | 20; 27; 30; 31 | BD-CW-SAMCO-ACE-LET-STR-019 - Request for Complete Set of IFC Drawings ¦ BD-CW-SAMCO-ACE-LET-STR-026 - Reply of Design Review ¦ BD-CW-SAMCO-ACE-LET-STR-029 - Design Review ¦ BD-CW-SAMCO-ACE-LET-STR-030 - Re: Design Review | Design review; Design review / criteria; IFC drawings / design review | High | Low | Contractor weak | Issue full report
BD-ACEPM-SAMCO-LET-021 | 22 | 10-Dec-2025 | Reporting notice | Periodic reports delay | BD-CW-SAMCO-ACE-LET-STR-033 | 34 | BD-CW-SAMCO-ACE-LET-STR-033 - Response to LET-021 Periodic Reports | Periodic reports / programme | Medium | Low | Contractor weak | Submit reports
BD-ACEPM-SAMCO-LET-022 | 23 | 28-Dec-2025 | Design clarification | Design review | BD-CW-SAMCO-ACE-LET-STR-026; BD-CW-SAMCO-ACE-LET-STR-030; BD-CW-SAMCO-ACE-LET-STR-034; BD-CW-SAMCO-ACE-LET-STR-040; BD-CW-SAMCO-ACE-LET-STR-052; BD-CW-SAMCO-ACE-LET-STR-063 | 27; 31; 35; 41; 53; 64 | BD-CW-SAMCO-ACE-LET-STR-026 - Reply of Design Review ¦ BD-CW-SAMCO-ACE-LET-STR-030 - Re: Design Review ¦ BD-CW-SAMCO-ACE-LET-STR-034 - Re: Design Review ¦ BD-CW-SAMCO-ACE-LET-STR-040 - Continuation of Works and Final Written Instructions ¦ BD-CW-SAMCO-ACE-LET-STR-052 - Project Status Update - Buildings B1 to B17 ¦ BD-CW-SAMCO-ACE-LET-STR-063 - Comparison of Design Issued 18-Mar-2026 vs 27-Oct-2025 | Design discrepancy / revised package; Design review; Design review / criteria; Project status / design / steel | High | Conditional low | Weak/uncertain | Submit remaining feedback
BD-ACEPM-SAMCO-LET-023 | 24 | 11-Jan-2026 | Incident closure | Water pipeline leakage | BD-CW-SAMCO-ACE-LET-STR-014; BD-CW-SAMCO-ACE-LET-STR-039 | 15; 40 | BD-CW-SAMCO-ACE-LET-STR-014 - Implications of Water Pipe Break ¦ BD-CW-SAMCO-ACE-LET-STR-039 - Water Pipeline Leakage and Its Impact on Project Works | Pipe breakage / leakage impact; Water pipeline leakage | Low |  | Contractor weak | Monitor pipe supports
BD-ACEPM-SAMCO-LET-024 | 25 | 22-Jan-2026 | Criteria clarification | Adopted design criteria | BD-CW-SAMCO-ACE-LET-STR-030; BD-CW-SAMCO-ACE-LET-STR-034; BD-CW-SAMCO-ACE-LET-STR-040; BD-CW-SAMCO-ACE-LET-STR-047; BD-CW-SAMCO-ACE-LET-STR-052; BD-CW-SAMCO-ACE-LET-STR-063 | 31; 35; 41; 48; 53; 64 | BD-CW-SAMCO-ACE-LET-STR-030 - Re: Design Review ¦ BD-CW-SAMCO-ACE-LET-STR-034 - Re: Design Review ¦ BD-CW-SAMCO-ACE-LET-STR-040 - Continuation of Works and Final Written Instructions ¦ BD-CW-SAMCO-ACE-LET-STR-047 - Additions to MOM - Coordination Meeting 19-Jan-2026 ¦ BD-CW-SAMCO-ACE-LET-STR-052 - Project Status Update - Buildings B1 to B17 ¦ BD-CW-SAMCO-ACE-LET-STR-063 - Comparison of Design Issued 18-Mar-2026 vs 27-Oct-2025 | Design discrepancy / revised package; Design review / criteria; MOM additions / commercial terms; Project status / design / steel | Medium | Low | Contractor weak | Continue verification
BD-ACEPM-SAMCO-LET-025 | 26 | 27-Jan-2026 | Contract interpretation | MEP first fix variation | BD-CW-SAMCO-ACE-LET-STR-016; BD-CW-SAMCO-ACE-LET-STR-027; BD-CW-SAMCO-ACE-LET-STR-032; BD-CW-SAMCO-ACE-LET-STR-035; BD-CW-SAMCO-ACE-LET-STR-041; BD-CW-SAMCO-ACE-LET-STR-049 | 17; 28; 33; 36; 42; 50 | BD-CW-SAMCO-ACE-LET-STR-016 - Clarification Regarding Coordination Responsibilities ¦ BD-CW-SAMCO-ACE-LET-STR-027 - Formal Rejection of Assigning MEP Works ¦ BD-CW-SAMCO-ACE-LET-STR-032 - Request for Complete Package for Coordination - TRA-007 ¦ BD-CW-SAMCO-ACE-LET-STR-035 - Response to LET-019 and VI-0003 ¦ BD-CW-SAMCO-ACE-LET-STR-041 - Critical Interface Issue on Critical Path ¦ BD-CW-SAMCO-ACE-LET-STR-049 - Response to LET-025 First Fix MEP Works | Critical MEP interface / tank base slab; MEP coordination / first fix; MEP first fix; MEP package / first fix; VI-0003 / flanges / MEP; VI-0003 / MEP works / flanges | High | Low | Employer strong | Execute variation
BD-ACEPM-SAMCO-LET-026 | 27 | 02-Feb-2026 | Variation clarification | Response to LET-025 | BD-CW-SAMCO-ACE-LET-STR-032; BD-CW-SAMCO-ACE-LET-STR-041; BD-CW-SAMCO-ACE-LET-STR-049 | 33; 42; 50 | BD-CW-SAMCO-ACE-LET-STR-032 - Request for Complete Package for Coordination - TRA-007 ¦ BD-CW-SAMCO-ACE-LET-STR-041 - Critical Interface Issue on Critical Path ¦ BD-CW-SAMCO-ACE-LET-STR-049 - Response to LET-025 First Fix MEP Works | Critical MEP interface / tank base slab; MEP first fix; MEP package / first fix | High | Conditional | Moderate if procedure followed | Execute and submit proposal
BD-ACEPM-SAMCO-LET-027 | 28 | 15-Feb-2026 | Commercial notice | Required breakdown delay | BD-CW-SAMCO-ACE-LET-STR-028; BD-CW-SAMCO-ACE-LET-STR-046 | 29; 47 | BD-CW-SAMCO-ACE-LET-STR-028 - Submission of Interim Payment Certificate No. 1 ¦ BD-CW-SAMCO-ACE-LET-STR-046 - Submission of Interim Payment Certificate No. 3 | IPC / payment; IPC / payment / breakdown | Low |  | Contractor weak | Submit breakdown
BD-ACEPM-SAMCO-LET-028 | 29 | 16-Feb-2026 | EOT rebuttal | Steel supply status | BD-CW-SAMCO-ACE-LET-STR-025; BD-CW-SAMCO-ACE-LET-STR-042; BD-CW-SAMCO-ACE-LET-STR-044; BD-CW-SAMCO-ACE-LET-STR-045; BD-CW-SAMCO-ACE-LET-STR-048; BD-CW-SAMCO-ACE-LET-STR-051; BD-CW-SAMCO-ACE-LET-STR-052; BD-CW-SAMCO-ACE-LET-STR-053; BD-CW-SAMCO-ACE-LET-STR-062; BD-CW-SAMCO-ACE-LET-STR-069 | 26; 43; 45; 46; 49; 52; 53; 54; 63; 70 | BD-CW-SAMCO-ACE-LET-STR-025 - Supply of Reinforcement Steel - Second Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-042 - Supply of Reinforcement Steel - Third Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-044 - Delay in Supplying Reinforcement Steel ¦ BD-CW-SAMCO-ACE-LET-STR-045 - Guarantee Cheque for Reinforcement Steel ¦ BD-CW-SAMCO-ACE-LET-STR-048 - Follow-up on Delay of Reinforcement Steel Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-051 - Reinforcement Steel Supply Status and EOT Entitlement ¦ BD-CW-SAMCO-ACE-LET-STR-052 - Project Status Update - Buildings B1 to B17 ¦ BD-CW-SAMCO-ACE-LET-STR-053 - Reinforcement Steel Order No. 2 Delay ¦ BD-CW-SAMCO-ACE-LET-STR-062 - Follow-up on Reinforcement Steel Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-069 - Follow-up on Reinforcement Steel Supply and Cumulative Project Impact | Project status / design / steel; Reinforcement steel supply; Reinforcement steel supply / guarantee cheque | High | Low/conditional | Weak to moderate | Submit mitigation plan
BD-ACEPM-SAMCO-LET-029 | 30 | 24-Feb-2026 | Protocol notice | Project status update | BD-CW-SAMCO-ACE-LET-STR-020; BD-CW-SAMCO-ACE-LET-STR-022; BD-CW-SAMCO-ACE-LET-STR-037; BD-CW-SAMCO-ACE-LET-STR-052 | 21; 23; 38; 53 | BD-CW-SAMCO-ACE-LET-STR-020 - Project Status Update - Buildings B1 to B17 ¦ BD-CW-SAMCO-ACE-LET-STR-022 - Project Status Update - Buildings B1 to B17 ¦ BD-CW-SAMCO-ACE-LET-STR-037 - Project Status Update - Buildings B1 to B17 ¦ BD-CW-SAMCO-ACE-LET-STR-052 - Project Status Update - Buildings B1 to B17 | Project status / design / steel; Project status updates | Low |  | Contractor weak | Use correct channels
BD-ACEPM-SAMCO-LET-030 | 31 | 15-Mar-2026 | Report comments | February 2026 MPR |  |  |  |  | Medium | Low | Contractor weak | Revise/resubmit MPR
BD-ACEPM-SAMCO-LET-031 | 32 | 19-Apr-2026 | Payment clarification | IPC settlement follow-up | BD-CW-SAMCO-ACE-LET-STR-028; BD-CW-SAMCO-ACE-LET-STR-038; BD-CW-SAMCO-ACE-LET-STR-046; BD-CW-SAMCO-ACE-LET-STR-047; BD-CW-SAMCO-ACE-LET-STR-054; BD-CW-SAMCO-ACE-LET-STR-055; BD-CW-SAMCO-ACE-LET-STR-056; BD-CW-SAMCO-ACE-LET-STR-059; BD-CW-SAMCO-ACE-LET-STR-068; BD-CW-SAMCO-ACE-LET-STR-075 | 29; 39; 47; 48; 55; 56; 57; 60; 69; 76 | BD-CW-SAMCO-ACE-LET-STR-028 - Submission of Interim Payment Certificate No. 1; BD-CW-SAMCO-ACE-LET-STR-038 - ACEPM Recommendation of Monthly Interim Payment No. 2; BD-CW-SAMCO-ACE-LET-STR-046 - Submission of Interim Payment Certificate No. 3; BD-CW-SAMCO-ACE-LET-STR-047 - Additions to MOM - Coordination Meeting 19-Jan-2026; BD-CW-SAMCO-ACE-LET-STR-054 - IPC Payment Status; BD-CW-SAMCO-ACE-LET-STR-055 - Actual Receipt Date of Cheque - IPC 1; BD-CW-SAMCO-ACE-LET-STR-056 - Submission of Interim Payment Certificate No. 4; BD-CW-SAMCO-ACE-LET-STR-059 - Submission of Interim Payment Certificate No. 5; BD-CW-SAMCO-ACE-LET-STR-068 - Follow-up on Settlement of IPCs; BD-CW-SAMCO-ACE-LET-STR-075 - Re: BD-ACEPM-SAMCO-LET-031 | IPC / payment; IPC / payment / breakdown; IPC / payment recommendation; IPC payment; IPC payment delay; MOM additions / commercial terms; Payments / IPCs / breakdown | Low |  | Contractor weak | Submit compliant IPCs
BD-ACEPM-SAMCO-LET-033 | 2 | 05-May-2026 | Contractual Response / Rejection | Re: Early Warning & Notification of Fact (pursuant to Sub-Clause 20.1) – Site Progress and Constraints for Buildings B1-B4 | BD-CW-SAMCO-ACE-LET-STR-071 | 2 | BD-CW-SAMCO-ACE-LET-STR-071 - Early Warning & Notification of Fact – Site Progress and Constraints for Buildings B1-B4 | Site progress / steel supply / RFI 17 / B1-B4 structural package | Medium | Low / Conditional | Contractor weak | Require a compliant detailed claim and supporting substantiation; preserve rights with formal contractual correspondence
BD-ACEPM-SAMCO-LET-034 | 34 | 06-May-2026 | Commercial Compliance / Deduction Notice | Submission of proof of payment for engineering stamps due on contractual works. |  |  |  | Engineering stamps / contractual deductions | Low | Low | Employer strong | Submit engineering-stamp receipts or accept deduction treatment before the next certificate
BD-ACEPM-SAMCO-LET-035 | 35 | 11-May-2026 | EOT rebuttal / steel supply position | Re: Notification of Reinforcement Steel Supply Status and Entitlement to Time Extensions | BD-CW-SAMCO-ACE-LET-STR-025; BD-CW-SAMCO-ACE-LET-STR-042; BD-CW-SAMCO-ACE-LET-STR-044; BD-CW-SAMCO-ACE-LET-STR-048; BD-CW-SAMCO-ACE-LET-STR-051; BD-CW-SAMCO-ACE-LET-STR-062; BD-CW-SAMCO-ACE-LET-STR-069; BD-CW-SAMCO-ACE-LET-STR-079 | 26; 43; 45; 49; 52; 63; 70; 80 | BD-CW-SAMCO-ACE-LET-STR-025 - Supply of Reinforcement Steel - Second Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-042 - Supply of Reinforcement Steel - Third Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-044 - Delay in Supplying Reinforcement Steel ¦ BD-CW-SAMCO-ACE-LET-STR-048 - Follow-up on Delay of Reinforcement Steel Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-051 - Reinforcement Steel Supply Status and EOT Entitlement ¦ BD-CW-SAMCO-ACE-LET-STR-062 - Follow-up on Reinforcement Steel Delivery ¦ BD-CW-SAMCO-ACE-LET-STR-069 - Follow-up on Reinforcement Steel Supply and Cumulative Project Impact ¦ BD-CW-SAMCO-ACE-LET-STR-079 - Reply to Notification of Reinforcement Steel Supply Status and Entitlement to Time Extensions | Reinforcement steel supply | High | Low / Conditional | Contractor weak | Submit mitigation plan, reconcile delivery dates, and maintain progress despite steel delivery completion
BD-ACEPM-SAMCO-LET-036 | 36 | 11-May-2026 | Delay notice / rate of progress | Failure to Achieve Section (1) Milestone within the Contractual Due Date | BD-CW-SAMCO-ACE-LET-STR-071; BD-CW-SAMCO-ACE-LET-STR-076; BD-CW-SAMCO-ACE-LET-STR-080 | 72; 77; 81 | BD-CW-SAMCO-ACE-LET-STR-071 - Early Warning & Notification of Fact (pursuant to Sub-Clause 20.1) – Site Progress and Constraints for Buildings B1-B4 ¦ BD-CW-SAMCO-ACE-LET-STR-076 - Notice of Claim - Impact of Revised Structural Drawings on Project Progress [Sub-Clause 1.9 / 8.4 / 20.1] ¦ BD-CW-SAMCO-ACE-LET-STR-080 - Response to Notice - Alleged Failure to Achieve Section (1) Milestone | Site progress / steel supply / RFI 17 / structural package discrepancy | High | Low / Conditional | Contractor weak | Submit recovery plan and assess milestone position against the actual steel / IFC / RFI impacts
BD-ACEPM-SAMCO-LET-037 | 37 | 17-May-2026 | Slow progress notice / monthly report comments | Notice of Slow Progress Rate and Comments on Monthly Progress Report - April 2026 | BD-CW-SAMCO-ACE-LET-STR-074 | 75 | BD-CW-SAMCO-ACE-LET-STR-074 - Re: Non-Compliance with Submission of Weekly Progress Reports. | Contractual submissions / reports | High | Low / Conditional | Contractor weak | Correct the monthly report, improve progress, and submit mitigation / recovery actions

## Issue Threads
Thread | SAMCO Ref(s) | 6 | Main Link | Priority | Next Action
Outstanding deliverables / tower cranes | STR-003 | LET-001; LET-002 | ACE notice followed by SAMCO rebuttal/updates | High | Confirm closed deliverables and baseline dependency
Survey / batching plant / Zone 2 | STR-004 | LET-003 | SAMCO raised site/survey issues; ACE issued clarification | Medium | Close survey/ramp/batching plant decisions
Contractual submissions / reports | STR-006; STR-033; STR-074 | LET-004; LET-018; LET-021; LET-030; LET-032; LET-037 | Submittals, programme, periodic reporting compliance, and slow-progress reporting comments. | High | Agree reporting baseline, submit overdue weekly / corrected monthly reports, and close the reporting-compliance and recovery-plan issues.
Water leakage / pipe breakage | STR-005; STR-007; STR-012; STR-013; STR-014; STR-039 | LET-005; LET-011; LET-023 | Contractor notices vs ACE closures/rejections | High | Separate closed incidents from substantiated rework/EOT claims
Ramp / access route | STR-008; STR-018 | LET-008; LET-014; LET-015 | Access responsibility and soil replacement delay | High | Determine access-route cost/time responsibility
Design verification / design criteria | STR-009; STR-019; STR-026; STR-029; STR-030; STR-034; STR-040; STR-047; STR-063; STR-064; STR-066; STR-067 | LET-006; LET-010; LET-020; LET-022; LET-024 | Design review, criteria, revised package and RFIs | High | Issue one coordinated design basis and close RFI/design-change impacts
Insurance | STR-021 | LET-007 | ACE rejection followed by SAMCO undertaking | Medium | Confirm compliant original insurance policies
MEP / first fix / flanges / VI-0003 | STR-016; STR-024; STR-027; STR-035; STR-041; STR-049; STR-072; STR-078 | LET-017; LET-019; LET-025; LET-026 | Scope dispute and first-fix coordination evolving into conditional execution under VO and MOM instructions | High | Finalize VO, BOQ, supervision, first-fix responsibilities, and close MOM action items.
Geotechnical / soil recommendations | STR-036; STR-037; STR-052 | LET-013 | Extra tests and geotechnical recommendations | Medium | Value instructed tests and close soil recommendations
Reinforcement steel supply | STR-010; STR-011; STR-025; STR-042; STR-044; STR-045; STR-048; STR-051; STR-053; STR-062; STR-069; STR-079 | LET-016; LET-028; LET-035 | Owner steel supply delay, mitigation deliveries, and time-impact entitlement | High | Reconcile delivery dates, mitigation quantities, third-batch requirements, and time impact.
Project status updates | STR-020; STR-022; STR-037; STR-052 | LET-029 | SAMCO routine status letters vs ACE protocol objection | Medium | Move routine status to reports/MOM; reserve letters for notices
Payments / IPCs / breakdown | STR-028; STR-038; STR-046; STR-054; STR-055; STR-056; STR-059; STR-068; STR-070; STR-075; STR-081 | LET-027; LET-031 | IPC submissions and payment-delay allegations versus ACE threshold response and project-constraint reservation | High | Reconcile IPC thresholds, due dates, certification timing, deductions, and interest exposure.
Weather notices | STR-031; STR-043; STR-058; STR-060; STR-061; STR-065 |  | Weather/safety records with no ACE response in table | Low | Keep weather log and prove critical-path effect if claimed
Waterproofing materials | STR-023; STR-073; STR-082 |  | Clarification and claim path on internal tank waterproofing scope, sequence, and warranty | High | Issue a final waterproofing decision and document its sequence, scope, and entitlement effects.
Concrete specification variation | STR-050 |  | Notice of variation for concrete strength/cement content | Medium | Locate Engineer determination and valuation
Site progress / steel supply / RFI 17 / structural package discrepancy | STR-071; STR-076; STR-080 | LET-033; LET-036 | SAMCO claim chain on structural-package discrepancies, steel supply, delayed technical response, and milestone impact | High | Convert the notice chain into a compliant substantiated claim with critical-path, milestone, and cause-effect evidence.
Retaining wall backfilling variation | STR-077 |  | Variation notice for retaining-wall backfilling with no ACE response in the current source table | High | Issue the VO, confirm valuation, and assess any critical-path effect from delayed instruction.
Engineering stamps / contractual deductions |  | LET-034 | ACE requested proof of engineering-stamp payment and reserved deduction from future certificates if proof is not submitted. | Medium | Submit the supporting receipts or confirm how deductions will be handled in the next certificate workflow.